Joint Operational Programme

Romania – Ukraine

2014-2020

Procedure for the evaluation and approval of large infrastructure projects selected through direct award

Abbreviations

CBC 			Cross Border Cooperation

EC			European Commission

ENI 			European Neighborhood Instrument

EU			European Union

JOP  			Joint Operational Programme

JTC			Joint Technical Secretariat

IR                                	Implementing Regulation

LIPs			Large Infrastructure Projects

MA 			Managing Authority

UA                              	Ukraine

MRDPAEF 	Ministry of Regional Development, Public Administration and European Funds

NGO			Non-Governmental Organisation

PS                                	Project summary

RDA            	Regional Development Agencies

RO			Romania

SME			Small and Medium Enterprises

TBD                            	To be determined

TA			Technical Assistance

TO			Thematic Objectives

Contents

Part one – Definition, Regulatory framework, Budget and duration	4

A)	Definitions	4

B)	Regulatory framework	4

C)	Budget	5

D)	duration	5

Part TWO – LIP criteria	6

PART THREE – Summary of the Evaluation and Approval process	15

PART Four – detailed Evaluation and Approval process	17

First step   – Development and approval of the LIP Project Summaries (PS)	17

Second step – Development, evaluation and submission of a full project application	20

ANNEXES	32

Annex 1 Mandatory activities for ensuring the visibility of the project and Programme	32

Annex 2 State Aid self-assessment	34

Annex 3 Job description (template)	41

Annex 4 Declaration and statements (templates)	42

4.1 Declaration by the Applicant	42

4.2 Partnership Statement	45

# Part one – Definition, Regulatory framework, Budget and duration

# Definitions

Project  – a series of activities defined and managed in relation to the objectives, outputs, results and impacts which it aims at achieving within a defined time period and budget. The objectives, outputs, results and impacts shall contribute to the priorities identified in the programme.

Large infrastructure projects – projects comprising a set of works, activities or services intended to fulfill an indivisible function of a precise nature pursuing clearly identified objectives of common interest for the purposes of implementing investments delivering a cross-border impact and benefits and where a budget share of at least EUR 2,5 million is allocated to acquisition of infrastructure.

Acquisition of infrastructure includes costs of works and services related to (re) construction, renovation, installation of infrastructure and costs of supplies related to the infrastructure component, including the purchase of fixed assets.

Technical documentation – is mandatory for execution of the infrastructure component according to the legislation of the country concerned, and may comprise documentation accompanying the building permit, such as the technical project, studies, execution details, consents, approvals, authorizations and agreements, if requested by the national laws of the respective country and mandatory to begin execution of the infrastructure

# Regulatory framework

- According to Article 41.1 of IR No.897/2014 “projects may be awarded without a call for proposals only in the following cases and provided this is dully substantiated in the award decision”:

- The body to which a project is awarded enjoys a de jure or de facto monopoly;

- The project relates to actions with specific characteristics that require a particular type of body based on its technical competence, high degree of specialization or administrative power.

- In order to qualify as a large infrastructure project, two other main conditions have to be fulfilled:

- The project proposal is part of the  final list of large infrastructure project (including the reserve proposals) included in the Programme pursuant to Article 41.2 of the ENI CBC IR;

- At all times, the proposals must fall within the LIP definition.

- According to the JOP, chapter 6.2, only Large Infrastructure Projects shall be selected through direct award. The list of LIPs is presented in Annex 2 of the JOP.

- The projects proposed for selection without a call for proposals shall be approved by the European Commission based on a two-step procedure, consisting in the submission of a project summary (PS) followed by a full application form (Article 41.4 of IR no 897/2014).

# Budget

According to the JOP provisions, the share of the Union contribution allocated to large infrastructure projects may not exceed 30%. In line with the JOP financial table, the overall community contribution to the Programme is 60,000,000.00 Euro, out of which a maximum of 18,000,000.00 euro (30%) is allocated for the large infrastructure projects.

TAKE NOTE THAT

If during the approval process by the JMC and by European Commission one or more selected LIPs are rejected, another project from the reserve list may start the procedures for selection, depending on the JMC decision, based on the financial resources made available.

TAKE NOTE THAT

A project may be rejected during the project preparation process provided that it does not fulfil the conditions set by the Programme (e.g. LIP criteria, eligibility, partnership, availability of co-financing, quality of technical documentation, etc.), or in case the beneficiaries make substantial changes within subsequent documentation that call into question the compliance with one or more of the exclusion, eligibility or selection criteria laid down in the programme, relevant regulation, or represent a modification of the initial project concept and objectives.

# duration

The planned duration for implementing a large infrastructure project shall be of maximum 24 months. However, in cases duly justified by the beneficiaries in the full application form, an initially planned duration of maximum 36 months may be accepted.

According to article 41.2 of ENI CBC IR the full applications (including the information referred to in article 43 of ENI CBC IR together with the justification for direct award) must be submitted to EC no later than 31 December 2017. Also, in line with article 18.1 and 18.2 of ENI CBC IR, the contracting of the large scale projects shall end before 30 June 2019 and all project activities financed by the programme shall end on 31 December 2022 at the latest.

# Part TWO – LIP criteria

- A LIP shall fulfill the following criteria, but not limited to:

- The bodies to which the project is awarded enjoys  a de jure or the facto monopoly;

- The project relates to actions with specific characteristics that require a particular type of body based on its technical competence, its high degree of specialization or its administrative power;

- The project comprise a set of works, activities or services intended to fulfill an indivisible function of a precise nature;

- The project pursues clearly identified objectives of common interest for the purposes of implementing investments delivering a cross-border impact and benefits;

- A budget share of at least 2.5 million Euros is allocated to acquisition of infrastructure.

The large infrastructure projects shall comply with all eligibility requirements outlined in the Joint Operational Programme and ENI CBC IR. Among these, special attention should be given to the eligibility criteria listed below.

- Applicants and Partners. Eligibility requirements

B.1	 Eligibility requirements for the Applicant and partners

The Applicant and all the partners in the project shall meet the following requirements:

- Be legal entities registered and located in the Programme area, namely in the Romanian counties of Suceava, Botoșani, Satu Mare, Maramureș, Tulcea or the Ukrainian oblasts of Zakarpattia, Ivano-Frankivsk, Odessa, Chernivtsi or Bucharest or Kiev, as major centres OR

- Be located outside the Programme area only in the conditions set at section B.1.1 Flexibility rule OR

- Be international organizations with a base of operation in the  Programme area or European Groupings of Territorial Cooperation regardless of their place of establishment, provided their geographic coverage is within the  Programme area, AND

- Be non-profit making organisations, AND

- Be directly responsible for the preparation and management of the project with their Partners, not acting as an intermediary, AND

- Have stable and sufficient sources of finance to ensure the continuity of the organisations throughout the project duration and to play a part in financing it AND

- Have no debts to the consolidated state budget or to the local budget in accordance with the national legislation.

- Not fall into any of the situation listed below:

- They are bankrupt or being wound up, are having their affairs administered by the courts, have entered into an arrangement with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or EU regulations.

- They or persons having powers of representation, decision making or control over them have been convicted of an offence concerning their professional conduct by a judgment of a competent authority of a Member State or Ukraine which has the force of res judicata.

- They have been guilty of grave professional misconduct proven by any means which the MA can justify including by decisions of the European Investment Bank and international organisations.

- They are not in compliance with their obligations relating to the payment of debts to the state or local budget in accordance with the legal provisions of the country in which they are established or with those of the country of the MA or those of the country where the contract is to be performed.

- They, or persons having powers of representation, decision making or control over them have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation, money laundering or any other illegal activity, where such illegal activity is detrimental to the European Union's financial interests.

- They are subject to an administrative penalty referred to in Article 109(1) of the EU Financial Regulation 966/2012.

- They are subject to a conflict of interests; the conflict of interests represents any circumstances that may affect the evaluation or implementation process, in an objective and impartial manner. Such circumstances may result from economic interests, political or national preferences or family connections.

- They are guilty of misrepresentation in supplying the information required by the Managing Authority as a condition of participation in the direct award or fail to supply this information.

- They have attempted to obtain confidential information or influence the evaluation bodies or the Managing Authority during the evaluation process of previous calls for proposals under the JOP Romania – Ukraine – Republic of Moldova 2007- 2013.

- They have an unpaid debt to the Managing Authority for any project financed under the RO-UA-MD ENPI-CBC Programme 2007-2013 at the date of contract signature. If The Managing Authority established debts (in the Debtors Ledger of the entity hosting the Managing Authority) for the Applicant and/or the Partners, the grant contract may be signed only if and after the situation of the debt is tackled  AND

- In case of organizations from Ukraine they must be able to open a dedicated bank account in a state-owned bank. Any organization, be it Applicant or Partner in a project, must be legally able to transfer/receive funds to/from foreign countries AND

- Have provable rights (ownership, long term rent, concession, administration, etc.) over each location (land/ building/space) where infrastructure over 1 MEUR is foreseen to be executed, valid until at least 2032. In case the respective Partner is not the owner, the written agreement of the owner saying that infrastructure may be executed and/or equipment may be installed/ used is needed.

TAKE NOTE THAT

The projects must address the priorities and indicative activities corresponding to the Thematic Objectives 7 Improvement and accessibility to the regions, development of transport and communication networks and systems and 8 Common challenges in the field of safety and security, as described by the Joint Operational Programme.

TAKE NOTE THAT

Non-eligibility of any of the project partners (Applicant or partners) leads to the non-eligibility of the entire project, irrespective of the fact that the minimum partner requirements are still met.

TAKE NOTE THAT

The Applicant or a partner cannot be changed and replaced with other organisation, and its share of the project cannot be taken over by other project partner during the evaluation and approval process (step 2 – full application form), as this would mean to change the project proposal after the submission deadline and thus to violate the principle of equal treatment.

B.1.1	 	Flexibility rule for the project partners

The Programme allows for participation of organizations from Romania or Ukraine registered outside the Programme area only if the following conditions are met:

- They do act as Partners in the project, not as Applicants (lead beneficiaries);

- Their participation is required by the nature and by the project objectives, and is necessary for its effective implementation;

- They meet all the eligibility requirements listed at points c) to j), section B1.

B.2 	Project location

Projects will be implemented in the Programme area (meaning core regions and major economic, social and cultural centers), as follows:

Core region:

In Romania – counties of Suceava, Botosani, Satu Mare, Maramures and Tulcea

In Ukraine – oblasts of Zakarpattia, Ivano-Frankivsk, Odessa and Chernivtsi

Major economic, social and cultural centers:

Bucharest, Romania or Kiev, Ukraine

B 2.1	Flexibility rule for project activities

Projects may be partially implemented outside the Programme area in exceptional cases, provided that the following conditions are both met:

- They are necessary for achieving the Programme objectives;

- They are in the benefit of the Programme area.

Only a total of 10% of the project budget (which includes grant and co-financing) may be spent outside the Programme area.

Summary of eligibility and flexibility rule

|  | Programme area | Outside the Programme area | Romania | Ukraine |
| --- | --- | --- | --- | --- |
| Applicant | yes | NO | yes | yes |
| Partner | yes | yes (1) | yes | yes |
| Partnership | - | - | and UA | and RO |
| Activities | yes | yes (2) | yes | yes |
| Project budget (total eligible costs) = grant +co-financing | - | (1) + (2) = max 10% of project budget | - | - |
| EU grant | max 90% of project budget |  |  |  |
| Co-financing | min 10% of project budget |  |  |  |

C) 	Eligibility of costs

The projects must comply with the non-profit principle: grants shall not have the purpose or effect of producing a profit within the framework of the project. Where a profit is made, the Managing Authority shall be entitled to recover the share of the profit corresponding to the Union contribution to the eligible costs actually incurred by the beneficiaries to carry out the project. For this purpose, profit shall be defined as a surplus of the receipts over the eligible costs incurred by the beneficiaries (Lead Beneficiary and partners), when the request is made for payment of the balance.

- In order to be eligible, the project costs must comply with the ENI CBC IR (article 48) and Programme provisions (section 6.9 Rules on eligibility expenditure);

- Forms of grant will be defined in the grant contracts, in accordance with article 47 of the ENI CBC IR.

C.1 	Eligibility requirements

Irrespective the sources of funding, either grant (EU contribution) or co-financing, the budget is both a cost estimate and a ceiling for "eligible costs". During the implementation, eligible costs must be based on real costs based on supporting documents (except for indirect costs, where flat-rate funding will apply).

Grant award decisions are always subject to the condition that the checking process which precedes the signature of the contracts does not reveal problems requiring changes to the budget (for instance arithmetical errors, inaccuracies or unrealistic costs and other ineligible costs, etc.).

The checks may give rise to requests for clarification by the Managing Authority and, moreover, may lead to modifications or reductions of the budget, meant to correct errors or inaccuracies.

The amount of grant and the share of the EU contribution as a result of the corrections made during contracting process may not be increased. It is therefore in the project's interest to provide a realistic and cost-effective budget, within the application form.

Eligible costs are actual costs incurred and paid by the project Partners which meet all the following criteria, which are to be included into the grant contract:

- They are incurred during the implementation period of the project. In particular:

- Costs of services and works shall relate to project activities performed during the implementation period. Costs of supplies shall relate to delivery and installation of items during the implementation period. Signature of a contract, placing an order or entering into any commitment for expenditure within the implementation period for future delivery of services, works or supplies after expiry of the implementation period do not meet this requirement. Cash transfers between the Partners may not be considered as costs incurred;

- Costs incurred should be paid before the submission of the final reports, except for the costs for expenditure verification corresponding to the final report, which may be incurred after the implementation period of the project. They may be paid afterwards, provided they are listed in the final report together with the estimated date of payment;

- If it is not foreseen otherwise in the national legislation of the project Partners, procedures to award contracts, may have been initiated and contracts may be concluded by the project partners before the start of the implementation period of the project, provided the provisions of ENI Implementing Regulation have been respected;

- They are included in the indicative overall budget for the project;

- They are necessary for the implementation of the project;

- They are identifiable and verifiable, in particular being recorded in the accounting records of the project partners and determined according to the accounting standards and the usual cost accounting practices applicable to the respective Partners;

- They comply with the requirements of applicable tax and social legislation;

- They are reasonable, justified and comply with the requirements of sound financial management, in particular regarding economy and efficiency;

- They are supported by invoices or documents of equivalent probative value;

- The compliance with the Programme Visual Identity requirements is ensured;

- Notwithstanding letter (a) above, costs related to technical documentations e.g. Feasibility Study or equivalent, Environmental Impact Assessment, and other technical documentation may be incurred before  the project implementation  period,  starting  with the approval date of the Programme, respectively 17 December, 2015;

- Notwithstanding letter (a) above, costs incurred after the date of submission full project application package are eligible provided that the need to start the project implementation before the contract signature has been demonstrated in the respective Application form.

C.2 	Eligibility rules for the preparatory costs

Article 48 (3) b) of the ENI CBC IR (Eligibility of costs) foresees that “a grant may be awarded retroactively for costs related to studies and documentation for projects including an infrastructure component”. The costs incurred with the feasibility study or equivalent, environment impact assessment, technical documentation which contribute to project preparation, evidence of ownership and building permit before the contract signature become eligible with the condition that a grant contract is signed between the Applicant and the MA. The costs may be reimbursed at the interim payment subject to the usual procedures for verification of expenditure. Please be aware that, in order to be eligible, the use of funds before the grant contract signature must observe the procurement procedure applicable at programme level.

The estimated costs for the feasibility study or equivalent, environment impact assessment, technical documentation which contribute to project preparation, evidence of ownership and building permit will not exceed 10% at project level of the costs of execution of the infrastructure (budget line 3.2), as evidenced in the feasibility study or equivalent and will be detailed within the Infrastructure budget breakdown (to be annexed to the Application Form).

In the case in which the institution acting as lead beneficiary/beneficiary possesses, according to the national legislation in force, the technical expertise to elaborate the studies needed for the project, these can be elaborated under the condition that the costs are not eligible under the project budget.

Article 48 (4) b) of the ENI CBC IR (Eligibility of costs) foresees that in order to “allow the preparation of strong partnerships, costs incurred before submission of the grant application by projects to which a grant has been awarded are eligible provided that the following conditions are also met”:

- they are incurred after the approval date of the Programme, respectively 17 December, 2015;

- they are limited to travel and subsistence costs for staff employed by the project Partners, provided they exceed neither the costs normally paid by the respective Partner according to its rules and regulations nor the rates published by the Commission at the time of the mission;

- they do not exceed EUR 3,000 EUR per project

C.3 	Eligible direct costs

When preparing the project budget, the following direct costs shall be considered:

- Staff assigned to the project, provided they relate to costs of activities which the organization would not carry out if the project was not undertaken, they do not exceed those normally borne by the respective organization unless it is demonstrated that this is essential to carry out the project, and they relate to actual gross salaries including social security charges and other remunerated-related costs.

- Travel and subsistence costs of staff, provided they exceed neither the costs normally paid by the organization according to its rules and regulations nor the rates published by the Commission at the time of the mission if reimbursed on the basis of lump sums, unit costs or flat rate financing.

- Purchase (only new) or rental for equipment and supplies specifically for the purpose of the project, provided they correspond to market prices. Distinction should be made between office equipment and endowment, and specialized equipment and endowment.

- Costs for infrastructure can include costs of works and services related to (re) construction, renovation, installation of infrastructure and costs of supplies related to the infrastructure component, including the purchase of fixed assets. They must be detailed in the Infrastructure budget breakdown (annexed to the Application form and serving only to evaluation purposes) and may also include costs for the technical documentation, taxes related to the provision of infrastructure and costs for site supervision.

- Costs entailed by contracts awarded by the Partners for the purposes of the project;

- Costs deriving directly from requirements imposed by ENI CBC Implementing Regulation and the project (such as information and visibility operations, evaluations, expenditure verification – only for Ukrainian organizations, translations)

Taxes, including VAT, will only be accepted as eligible costs when the Applicant or its Partners can show they cannot reclaim them according to their national legislation. According to the Framework Agreement between the European Commission and the Government of Ukraine, taxes, duties or other charges (including VAT) are excluded from the Community financing. Once the grant contract is signed, the Ukrainian beneficiaries should seek for registration at the Ministry of Economy and Trade in order to be exempted from the VAT.

With the view to ensure that the project budget is cost-effective, ceilings must be applied for some direct costs, as follows:

- Costs for the feasibility study or equivalent, environment impact assessment, technical documentation which contributes to project preparation, evidence of ownership and building permit must not exceed 10% of the costs (at project level) of execution of the infrastructure (budget line 3.2); in the case in which the amount needed for the development of technical documentation exceeds 10%, the difference is not eligible under the project budget and will be supported form the beneficiaries own sources.

- Costs of vehicles purchased for the project management shall not exceed EUR 18,000 per vehicle (this amount does not include  insurance, maintenance or minor repairs costs related to the purchased vehicle which may be nevertheless included at this budget line);

- Subsistence costs shall exceed neither the cost normally paid by the beneficiary entity  according to the national legislation in force, nor the rates published by the Commission at the time of holding that event;

- Costs for communication and visibility actions related to project/ Programme promotion shall amount to minimum 2% of the total direct eligible costs of the project, excluding costs for infrastructure/works (heading 3 in the project budget) and costs of communication and visibility actions (heading 7 in the project budget). The project shall foresee to carry out at least the minimum communication and visibility actions required by the Programme (see Annex 1).

- Costs for travel and subsistence of staff employed by the project Partners incurred before the full project application package was submitted, must not exceed 3,000 EUR per project.

C.4 	Contingency reserve

A contingency reserve not exceeding 10% of the costs of execution of the infrastructure (budget line 3.2) may be included in the project budget in order to allow adjustments in case of unforeseen circumstances. The reserve can only be used with the prior written authorization of the Managing Authority.

C.5 	Eligible indirect costs (administrative costs)

The indirect costs incurred during implementation may be eligible for a flat-rate funding of no more than 7% of the total amount of direct eligible costs, excluding costs of infrastructure/works (heading 3 in the project budget).

Indirect costs are eligible provided that they do not include costs assigned to another budget heading. The Managing Authority may ask to justify the requested percentage before contracting. However, once the flat-rate has been fixed in the grant contract, no supporting documents need to be provided at the reports with payment request, but they could be requested for verification, if necessary.

Indirect costs may include office costs (including rental), electricity, heating, phone, cleaning, salaries for the staff supporting project implementation (e.g. accountant, driver, secretary etc.), postal services, financial services, archiving, security services etc., if they were not provided under other budget lines.

C.6 	Contribution in kind

Contributions in kind are not considered actual expenditure and are not eligible costs. The contributions in kind may not be treated as co-financing by the project Partners.

Notwithstanding the above, if the project foresees the contributions in kind, they must be provided as described in the Application form, but will not be considered as eligible expenditure.

C.7	 Ineligible costs

The following costs are not eligible:

- Debts and debts service charges (interest);

- Provisions for losses or potential future liabilities;

- Costs declared by the beneficiaries and covered by another project or programme from any other sources;

- Purchases of land or buildings;

- Purchase of used equipment or vehicles;

- Purchase of equipment or vehicles in leasing

- Exchange-rate losses;

- Duties, taxes, charges, including VAT, except where non-recoverable under national legislation, unless otherwise provided in appropriate provisions negotiated with Ukraine;

- Loans to third parties;

- Fines, financial penalties and expenses of litigation;

- Contributions in kind as defined in article 14(1) of the ENI Implementing Regulation;

- Costs exceeding the threshold of 10% of the total project budget to be used by Beneficiaries, other than the Lead Beneficiary, located outside the Programme area, and for activities implemented outside the Programme area by any Beneficiary, including the Lead Beneficiary.

# PART THREE – Summary of the Evaluation and Approval process

| No. | Step | Activities to be carried out | Responsible body | Indicative time-frame |
| --- | --- | --- | --- | --- |
| 1. | Project summary | Elaboration of project summaries | - Lead beneficiaries & partners - MA & JTS (support and process coordination) | 2 months after the approval of the evaluation and approval procedure |
|  |  | Verification of project summaries | - JTS (administrative and eligibility verification) - MA (overall coordination & qualitative check) | 1 month |
|  |  | Approval of the project summaries | - JMC | 1 month after the submission of the final version of the project summary |
|  |  | EC confirmation of the LIP project summaries | - EC | 2 months |
| Estimated indicative timeline: up to 6 months |  |  |  |  |
| 2. | Full project application package | Elaboration of full project application package, including documents required by art.43 (2) of ENI CBC IR | - Lead beneficiaries & partners - MA & JTS (support and process coordination) | 6 months |
|  |  | Administrative and eligibility check of the full project application package | - JTS (administrative and eligibility check ) - NAs (eligibility check) - MA (overall coordination) | 1 month |
|  |  | Evaluation of the full project application package (technical and financial assessment, and assessment of documents required by art.43 (2) of ENI CBC IR) and filling in EC checklist | - MA and JTS - NAs (support for filling in EC checklist) | 1 month |
|  |  | Approval of the full project application package | - JMC | 10 working days from the submission of the full project application package and EC checklist |
|  |  | Final approval by the EC | - EC | 2 months |
| Estimated indicative timeline: up to 1 year |  |  |  |  |
| 3. | Contracting phase | Submission of documents necessary for the grant contract signature | - Lead beneficiaries & partners - MA & JTS (support and process coordination) | In line with the Programme contracting procedure. The deadline set by the ENI CBC IR for contracting LIPs is 30 June, 2019 |
|  |  | Signature of the grant contract | - Lead beneficiary & partners - MA |  |
| 4. | Project Implementation | The project is implemented in line with the approved activities and results. | - Lead beneficiaries & partners - MA & JTS & NA & CCP | All financed activities shall end on 31 December 2022 at the latest. |

# PART Four – detailed Evaluation and Approval process

The Managing Authority shall coordinate the overall evaluation and approval process. The Joint Technical Secretariat will provide support to the MA during each step outlined below .The large infrastructure projects shall be approved by the JMC and the European Commission based on a two-step approval procedure as follows:

### First step   – Development and approval of the LIP Project Summaries (PS)

- Project fiche

The project fiches are included as annexes to the JOP. They have already been agreed by the participant countries and approved by the European Commission. Consequently, they will constitute the starting point for developing of the future large infrastructure projects.

TAKE NOTE THAT

The project partners, the overall project objective and the main activities presented in the approved project fiches will be fully considered by the beneficiaries when preparing the subsequent documents (project summary and full application).

Modification of the data presented in the project fiche may only be admitted when duly justified. In no circumstances the modifications made may alter the initially stated project objectives and the compliance with the LIP criteria.

The approved European financial contribution cannot be increased.

- Project summary

The Project Summaries and the corresponding annexes shall be elaborated by the beneficiaries and they should comply with the calendar set by JMA and JTS at Programme level. The MA and JTS support during the process of drafting the project summaries will be given with due respect of the principle of equal treatment of applicants.

In the case in which the beneficiaries do not comply with the deadlines set by the management structures, the MA may invite, with prior approval of the JMC, and based on the financial resources made available, other applicant from the reserve list to start the preparation of the project summary.

The main content of project summary shall include:

- Identification of the beneficiaries and designation of the lead beneficiary, providing guarantees of its competence in the domain concerned by the project as well as its administrative and financial management capacity;

- Justification of the lead beneficiary and beneficiaries de jure or de facto monopoly and/or justification that the project is of specific characteristics that require a particular type of body on account of its technical competence, its high degree of specialization or its administrative power;

- An analysis of the problems and needs justifying the project, taking into account the programme strategy and its expected contribution to address the corresponding priority of the JOP;

- An assessment of cross border impact and benefits;

- Short description of the prerequisites needed for ensuring the project sustainability.

- Project description

The project description will contain at least the following information:

- The general and specific objectives,

- Compliance with the JOP priorities,

- Expected results,

- Project contribution to the Programme expected results,

- Project contribution to the EU strategies and programmes,

- Geographical coverage,

- Target groups and final beneficiaries,

- Main activities* to be carried out,

- When project is partially implemented outside the programme area, explanation of how these corresponding activities will contribute to the programme objectives and will be made for the benefit of the programme area,

- Overall indicative budget** of the project and the indicative budget per partners, and per infrastructure component,

- Project duration,

- Declaration by the applicant and partnerships statements regarding the acknowledgment of the beneficiaries’ responsibilities within the project,

- If available***, submission of additional documents which can demonstrate the readiness of project implementation: feasibility study, the environment impact assessment, evidence of ownership by the beneficiaries or access to land, building permit, etc.

* The detailed activities will be outlined within the Application Form. In comparison with the project summary, only minor modifications to the Application Form are allowed on case by case basis, provided that the project's scope/ activities and objectives are to remain the same and the reasons provided by project partners are well grounded and justified.

** The project budget will be fully detailed in the corresponding section from the Application Form. In comparison with the project summary, only minor modifications to the budget, on case by case basis, are allowed, and/or to transfer the sums between partners The ENI financial allocation to the project cannot be increased.

*** Submission of these documents at the stage of the project summary is not mandatory but will only provide insight on the stage of project preparation. However, these documents will be mandatory to be attached to the full application.

The template for the Project Summary is annexed to the present Procedure and is part of it.

- Administrative and eligibility verification

After the final submission of the project summaries, the JTS will verify the documentation from an administrative point of view and, if needed, will ask for clarifications. The MA is entitled to request qualitative clarifications. Considering the LIPs criteria, the NAs will be required to give their opinion on the eligibility of entities (applicants and/ or partners) located on the national territory.

- JMC approval

The project summaries are submitted for approval to the JMC. With the purpose of providing to the JMC a full description of the project evolution, the MA will provide the description of the project track, the encountered problems and its corresponding quality.

The JMC decision may be accompanied by a written recommendation, reflecting how each proposal complies with the criteria presented in the JOP/LIP procedure/ guidelines. The JMC decision can:

- Further recommend the project summary to be submitted to European Commission for the final approval OR

- Reject the project if the proposal does not fully comply with the LIP criteria/ LIP procedure/ other relevant criteria.

Note: the project summaries will be submitted to the JMC in the order of their readiness.

- EC approval

If approved by the JMC, the project summaries are submitted for approval to the European Commission. EC shall notify its decision to the Managing Authority within two months of the document submission date.

Important! If during the approval process by the JMC or European Commission one or more selected LIPs are rejected, another project from the reserve list may start the procedures for selection, depending on the JMC decision, based on the financial resources made available.

### Second step – Development, evaluation and submission of a full project application

- Preparation and content of the full project application package

Further the approval of the project summaries, the applicants will elaborate and provide the full project application package which includes:

- the Application Form and its annexes,

- the feasibility studies or equivalent, environmental impact assessment, evidence of ownership, building permit,

- declarations of the applicant and partnership statements required by the programme and

the technical documentation.

During this preparation process both the JTS and the MA will provide assistance and support to the project beneficiaries (e.g. trainings, meetings with the beneficiaries, etc.).

For the development of the full project application package the project partners will have at their disposal a maximum of 6 months and must not go over the deadlines set by the management structures. Failing to fulfill this condition, the MA may invite, with prior approval of the JMC, and based on the financial resources made available, other applicant from the reserve list to start the process of preparation, provided that the remaining time until the deadline set by ENI CBC IR (31.12.2017) allows it.

The template of the Application Form is provided by the MA. The Application Form, besides sections 1-5/ a-l regarding the project summary, shall contain at least the following information

- The logical framework;

- An assessment of the sustainability of the project’s expected results after completion;

- Objectively verifiable indicators;

- The expected implementation period of the project and detailed work plan;

- An analysis of the effects of the project on the cross-cutting issues referred to in point 3(d) of article 4 of ENI CBC IR, where relevant;

- The project implementation requirements, including the following:

- Description of the project management and implementation structure;

- Arrangements among beneficiaries in line with article 46 of ENI CBC IR;

- Monitoring and evaluation arrangements;

- Information and communication plans, in particular, measures to acknowledge the Union support to the project;

- Detailed financial plan (annex 5) and budget per project and per partners;

- A detailed description of the infrastructure investment and its location; if the case applies, the applicant can demonstrate, within the Application Form, section Work plan per Groups of activities, the need to start the project before the contract is signed, and after the submission of the full project application package.

- A detailed description of the capacity building component of the project, except in duly justified cases;

- A full feasibility study or equivalent carried out, including the options analysis, the results, and independent quality review for the entire infrastructure component, or separate feasibility studies or equivalent from each beneficiary executing a part of the infrastructure component of more than 1 MEUR;

- An assessment of its environmental impact for the entire infrastructure component, or separate environmental impact assessments from each beneficiary executing a part of the infrastructure component of more than 1 MEUR according to the national legislation in force and in compliance with the Directive 2011/92/EU of the European Parliament and of the Council and, for the participating countries which are parties to it, UN/ECE Espoo Convention on Environmental Impact Assessment in a Transboundary Context of 25 February 1991;

- Evidence of ownership or access to the land for each location (land/ building/ space) where a beneficiary will execute a part of the infrastructure component of more than 1 MEUR;

- Building permits for each beneficiary executing a part of the infrastructure component of more than 1 MEUR.

- Documents proving the eligibility of the beneficiaries.

In case of a beneficiary needing to execute a part of the infrastructure component of less than 1 MEUR, the feasibility study or equivalent, the environment impact assessment and the building permit, if requested by the national law of the respective country and is mandatory to begin execution of the infrastructure, shall be submitted within 6 months from the start date of implementation, but no later than submission of the interim payment request, in English and in national language, as photocopies certified “According to the original”, stamped and signed by the legal representative. This provision will be included in the grant contract and, in case the project fails to comply, the payment of the interim installment will not be made.

Any project shall organize its activities into maximum 5 Groups of Activities (GAs), out of which the following are mandatory:

(GA0) Project preparation details the preliminary actions taken until submission of the full project application package, including building or enhancing the project partnership, identification and involvement of project stakeholders, development of the feasibility study, of the environmental impact assessment and obtainment of authorizations/permits/approvals needed for executing the infrastructure component;

(GA1)Project management refers to, inter alia day-to-day arrangements for project implementation and coordination among partners, use of resources, compliance with the grant contract requirements, risks analysis and possible measures.

(GA2) Information and communication plan describes activities meant to display the project results and acknowledge the Union support towards the final beneficiaries and the general public. Annex 1 provides information about the minimum inventory of information, promotion and communication activities to be undertaken at project level.

(GA3) To be defined i.e. group of activities defined by the beneficiaries in line with the project activities

(GA4) Infrastructure explains the need for the infrastructure with the view to achieve project objectives and results (as presented in the Project Summary), the benefits envisaged, and gives details on the technical specifications of the infrastructure and the necessary technical documentation.

Moreover, the capacity building activities should be clearly described in the corresponding Groups of Activities as they are mandatory according to the Implementing Rules.

Concerning the budget content take note that:

  - Details about the costs envisaged by the project must be included in the Justification sheet to be annexed to the Application Form.

  - The costs of infrastructure shall be detailed in Infrastructure Budget Breakdown to be annexed to the Application Form.

- Submission of the full project application package

The Application Form, its annexes and the accompanying documents, including the electronic version on DVD of the whole package, shall be submitted in a sealed envelope in 1 original and 1 copy “according to the original” by registered mail, private courier service or by hand delivery at the address below:

Regional Office for Cross-border cooperation Suceava

Romania - Ukraine

8A, Bistritei Street, 1st floor (Building DAE Office Center no. 1), 720274, Suceava

Suceava County – Romania

The DVD will include a list detailing the documentation comprised in the full project application package, listing as much as possible the content.

TAKE NOTE THAT

Any document sent as hard-copy, including the Application Form, shall be signed and stamped by the legal representative of the beneficiary to whom the respective document pertains.

The Application Form shall be signed and stamped by the legal representative of the Applicant. The individual budgets must be signed and stamped by the legal representatives of the respective partners.

The Applicants must ensure themselves that the final version of the Application Form, its annexes and the accompanying documents are checked for correctness and completeness.

Submission of the full project application package must not go over the deadlines set by the management structures. Failing to fulfill this condition, the MA may invite, with prior approval of the JMC, and based on the financial resources made available, other applicant from the reserve list to start the process of preparation, provided that the remaining time until the deadline set by ENI CBC IR (31.12.2017) allows it.

- Additional documents according to art.43 (2) of ENI CBC IR:

  - Feasibility study (FS) or equivalent

The FS or equivalent shall be prepared according to the JOP requirements and elaborated according to the national rules of the country where the infrastructure is located

Depending on the project, it will be up to the applicant to submit a joint feasibility study drawn up for the entire infrastructure component or separate feasibility studies by each beneficiary executing a part of the infrastructure component of more than 1 MEUR. The FS or equivalent shall be submitted in national language and English translation, as photocopy certified “According to the original”, signed and stamped by the legal representatives.

It is recommended that the FS/equivalent contains at least the following elements:

- General information about the project (description of the investment, technical data of the investment – area and location, the legal status of the land/building, site surveys, the main characteristic of the proposed constructions, project schedule);

- Option analysis, the results and independent quality review;

- Estimated costs for the investment;

- Main technical and economic indicators, authorizations and agreements (type of documentation required by the different national legislations), drawings.

  - Environment impact assessment (EIA)

The common principle of EIA (Directive 2011/92/EU of the European Parliament and of the Council of 13 December 2011 on the assessment of the effects of certain public and private projects on the environment) is to ensure that projects likely to have significant effects on the environment because of their nature, size and location are made subject to an EIA, prior to their approval.

The EIA shall describe and assess the direct and indirect effects of a project on the following factors:

- Human beings, fauna and flora;

- Soil, water, air, climate and landscape;

- Material assets and the cultural heritage;

- Interaction among the above mentioned factors.

The Environment Impact Assessment and the Notice issued by the responsible environment authority of the respective country based on the EIA study shall be submitted by each Partner executing a part of the infrastructure component over 1 MEUR, in national language and English translation, as photocopy certified “According to the original”, signed and stamped by the legal representative. In the case of infrastructure below 1 MEUR, the EIA must be submitted within 6 months from the start date of implementation, but no later than submission of the interim payment request.

However, where requested by national legislation, public consultations will be conducted in the frame of the assessment of the environmental impact and the outcomes will be also provided, together with a justification of how the concerns have been addressed in the project.

In case the relevant authorities in each country decide that the assessment is not required for a certain project, the applicant and/ or partners executing that part of the infrastructure component shall submit the relevant documents issued by this responsible institutions proving that the environment impact assessment is not required – as photocopies certified “According to the original”, stamped and signed by the legal representative, in national language and English translation.

  - The evidence of ownership by the beneficiary or access to the land and to the infrastructure to be realized/ rehabilitated/ improved.

Each beneficiary executing a part of the infrastructure component of more than 1 MEUR must provide documents attesting the ownership or availability to use the respective location (land/building/space).

Location of the proposed infrastructure shall be identified by the following means:

- Small scale plans (e.g. 1:10.000) showing the location;

- Large scale plans (e.g. 1:500 or less) showing approximate size and outlines of main structures;

For each location where a part of the infrastructure component of more than 1 MEUR is to be executed, the typology of the documents to be provided is:

- legal acts stating the rights over each location (land/ building/space) where the infrastructure is foreseen to be executed, valid at least until 2032 (ownership, long term rent, concession, administration, etc.) – in national language and English translation, as photocopies certified “According to the original”, signed and stamped by the legal representatives AND

- documents showing registration of each location (land/ building/space) where the infrastructure is foreseen to be executed in the relevant public registers – in national language and English translation, as photocopies certified “According to the original”, signed and stamped by the legal representatives, AND

- statements that each location (land/ building/space) where the infrastructure is foreseen to be executed is free of any encumbrances, is not the object of a pending litigation, is not the object of a claim according to the relevant national legislation – in national language and English translation, as photocopies certified “According to the original”, signed and stamped by the legal representatives.

In case the respective Partner(s) is not the owner of the location (land/building/space), the agreement of the owner, stating that the infrastructure component may be executed– in national language and English translation, as photocopies certified “According to the original”, signed and stamped by the legal representative.

An exception is made only for the parts of investments regarding passages that over cross or under cross the railroad infrastructure, when only the agreement of the railroad administrator for the execution of the works and access for usage and maintenance of the investment, valid at least until 2032 - in national language and in English translation, as photocopies certified “According to the original”, signed and stamped by the legal representatives. The conditions comprised in the agreement of the railroad administrator shall be respected.

In case of a beneficiary needing to execute a part of the infrastructure component of less than 1 MEUR or to install/use equipment over 60,000 EUR, the documents listed from (a) to (c) above must be provided for each such location (land/building/space) before the grant contract signature.

  - Building permits

The building permits shall be submitted, in line with the national legislation. In consultation with the National Authorities, it shall be established which is the document equivalent to the building permit.

In case the building permit or equivalent is not required by the national legislation, relevant excerpts from the legal framework will be provided.

In exceptional and duly justified cases, the Managing Authority may accept a later submission of the building permit as follows:

- Prior with at least one month from the deadline for submission of the full application form and technical documents the applicant/ partners officially informs the MA and justifies any exceptional circumstance (s) that could impede the delivery of the building permit.

- The MA decision regarding the acceptance of a later submission of the building permit will be based on the existence of exceptional circumstances fully justified and explained.

  - Technical documentation (other than FS and EIA)

It may comprise documentation accompanying the building permit, such as technical project, any other studies, execution details, consents, approvals, authorizations and agreements, if requested by the national laws of the respective country and mandatory to begin execution of the infrastructure and must be fully developed by each Partner executing a part of the infrastructure component of more than 1 MEUR.

Technical documentation should be available upon request at the time of submitting the full project application package - in English language, as photocopies certified “According to the original”, signed and stamped by the legal representatives.

TAKE NOTE THAT

The EC expects that the building permit and the technical documentation is submitted along with the full project application package. In the case the building permit is not requested by the national legislation for a particular type of infrastructure, the specific case should be explained and properly documented (for instance, by providing the legislative norm according to which the building permit is not required in the particular case).

In the case in which the building permit is not provided or delayed beyond the moment of the submission of the full project application package by the MA to the European Commission – December 2017, the project is at limited risk to not be approved by the EC. This risk falls exclusively in the responsibility of the beneficiaries.

- Documents regarding the eligibility of the Applicant and partners.

The following documents shall be provided by all the Partners:

- Statutes or other relevant document for the Applicant and each project Partner – photocopies certified “According to the original”, stamped and signed by the legal representative, in national language and English translation AND

- Profit and loss accounts, and the balance sheets or other relevant fiscal documents for the last year for which the accounts have been closed, for the Applicant and each project Partner – photocopies certified “According to the original”, stamped and signed by the legal representative, in national language and English translation AND

- Certificates of fiscal registration of the Applicant and each project Partner – photocopies certified “According to the original”, stamped and signed by the legal representative, in national language and English translation AND

- State Aid self-assessment (Annex 2) AND

- Valid certificates issued by the competent state authority in each participating country proving that the Applicant and its Partners have fulfilled their obligations related to the payment of debt to the consolidated state budget in accordance with the legal provisions of the country in which they are established - photocopies certified “According to the original”, stamped and signed by the legal representative, in national language and English translation AND;

- Valid certificates issued by the competent local authority in each participating country proving that the Applicant and its Partners have fulfilled obligations relating to the payment of debts to the local budget in accordance with the legal provisions of the country in which they are established – photocopies certified “According to the original”, stamped and signed by the legal representative, in the national language and in English translation; When this type of document is not available, a self-declaration in English, signed by the legal representative of the applicant / partner stating that obligations relating to the payment of debts to the local budget are fulfilled should be provided;

- Declaration by the Applicant and Partnership Statements (Annex 4) - in original, in English

- Job descriptions for all the functions listed in the Application Form – in original, in English (Annex 3)

The Applicants are requested to attach the supporting documents after the Application Form and its annexes, in the sequence described above, bound them together in the way that pages cannot not be taken away from a whole set. The very first page of the proposal should be visible, where [Name of the Applicant] and [Thematic Objective] and [Priority] should be written.

Where documents are in the national language, an English translation of the relevant parts reflecting the main content and proving the eligibility of the Applicant and his partners is required. This translation must bear “According to the original”, be signed and stamped by the legal representatives and will prevail for the purpose of the eligibility check.

- Information concerning procurements:

For procurement of goods, works or services by a beneficiary (including those for acquiring the services for the elaboration of the documents prior the grant contract signature - i.e. feasibility study, environmental impact assessment, etc. - needed for the submission of the full project application package), the applicable rules that must be observed are those set out by the ENI CBC IR no.897/ 2014 and the Financing Agreement between EC and Ukraine as follows:

- The Romanian beneficiaries - article 52 paragraph 1 of ENI CBC IR no. 897/ 2014

- Ukrainian beneficiaries – article 52 paragraphs 2 and 3 & articles 53 to 56 ENI CBC IR no. 897/ 2014 and applicable rules of the Financing Agreement

- Evaluation of the full project application package

Once the applicants submit the full project application packages, they are administratively verified by the JTS and if the case, clarifications are requested.

Each project will be analyzed by the MA and JTS. At all times, qualitative and technical clarifications from the applicant may be requested.

The NAs will be required to give their opinion on:

- the eligibility of entities (applicants and/ or partners) located on the national territory;

- Compliance with the national requirements of the Feasibility Study or equivalent;

- Compliance with the State Aid rules;

- Compliance of Environment Impact Assessment with the national legislation;

- Project’s compliance with equivalent national legislation and with the contents on the matter of any bilateral agreement (Association, Framework or Partnership agreements)

If necessary, in order to conclude the evaluation, the MA may organize joint meetings with the NA representatives.

TAKE NOTE THAT

The project will be analysed through the use of the attached EC checklist. The checklist also represents an important self-assessment tool for the beneficiaries as to make sure that all LIP requirements are fulfilled at the moment of the submission of the full project application package, including the technical documentation.

- JMC  final approval

The full project application package, along with the EC checklist is submitted for approval to the JMC, along with the MA recommendations and conclusions. The MA recommendations will regard the track of the project, the encountered problems and its corresponding quality.

- EC final approval

If approved by the JMC, the full project application package is submitted for approval to the European Commission. EC shall notify its decision to the Managing Authority within two months of the document submission date.

Please note that the final deadline set by the relevant EU regulation for the submission of the full project application package and the technical documentation is 31st of December 2017.  Non-compliance with the above term will lead to automatic exclusion of the project from the selection process.

- Preparing the grant contract signature

Before signing the grant contract, all the projects shall undergo a contracting procedure.

After being notified about the EC’s decision, the Applicant has to submit to the JTS/ MA mainly the following documents:

a) Partnership Agreement stamped and signed by the legal representatives of the Applicant and of each Partner – as original. All partners in a project must sign a partnership agreement that stipulates the rights and duties of the partners before the signing of the grant contract with the MA. A model of partnership agreement will be made available to the LIP beneficiaries. The partners may decide to stipulate additional provisions provided that the respective provisions do not contradict and are fully in line with those mentioned in the model partnership agreement.

b) Financial Identification Forms for the accounts specially opened for the project in EUR and in the national currency, for the Applicant and for all the Partners who are responsible for managing a share of the project budget – in original, in English. A model of Financial Identification Form will be made available to the LIP beneficiaries.

c) Decision of the empowered bodies of the Applicant and of all the project Partners, stating the amount and percentage of co-financing to be provided and spent during the implementation period of the project, as well as any ineligible expenditure or any other costs necessary for the project implementation – in original or as legalized copies, in national language and in authorized English translation.

d) Legal entity sheets for the Applicant and all the project Partners, as originals, signed and stamped by the legal representatives. A model of Legal entity sheet will be made available to the LIP beneficiaries.

e) Valid certificates issued by the competent state authority in each participating country proving that the Applicant and its Partners have fulfilled their obligations related to the payment of debt to the consolidated state budget in accordance with the legal provisions of the country in which they are established - photocopies certified “According to the original”, stamped and signed by the legal representative, in national language and English translation;

f) Valid certificates issued by the competent local authority in each participating country proving that the Applicant and its Partners have fulfilled obligations relating to the payment of debts to the local budget in accordance with the legal provisions of the country in which they are established – photocopies certified “According to the original”, stamped and signed by the legal representative, in the national language and in English translation. When this type of document is not available, a self-declaration in English, signed by the legal representative of the applicant / partner stating that obligations relating to the payment of debts to the local budget are fulfilled should be provided;

g) Beneficiary’s Statement in the format to be provided by the JTS, in original, in English, signed and stamped by the legal representative of the Applicant.

In case a beneficiary is intending to execute a part of the infrastructure component of less than 1 MEUR or to install/use equipment over 60,000 EUR, the following documents shall also be submitted for each location:

g.1) legal acts stating the rights over each location (land/ building/space) , valid at least until 2032 (ownership, long term rent, concession, administration, etc.) – in national language and English translation, as photocopies certified “According to the original”, signed and stamped by the legal representatives AND

g.2) documents showing registration of each location (land/ building/space) in the relevant public registers – in national language and English translation, as photocopies certified “According to the original”, signed and stamped by the legal representatives, AND

g.3) statements that each location (land/ building/space) is free of any encumbrances, is not the object of a pending litigation, is not the object of a claim according to the relevant national legislation – in national language and English translation, as photocopies certified “According to the original”, signed and stamped by the legal representatives.

All the documents must show legible stamps, signatures and dates. The English translation should bear “According to the original”, be signed by the legal representative, and stamped.

Before signing the contracts, other documents may be requested by the JTS/MA (e.g. proof that there are no debts to the Programme budget, proof that the VAT is non-recoverable from other sources etc.) and on-the-spot visits shall also take place.

In order to verify the information and documents provided by the project partners during the evaluation process in what concerns the location(s) where the project will be implemented and/ or the infrastructure component(s) will be executed, in order to prevent possible fraud or contracting errors, the JTS will perform pre-contracting on-site visits at the Beneficiaries and at all the locations where infrastructure shall be executed, irrespective the Partner concerned. The purpose of the on-site visits will be, inter alia, to check the documents necessary for the signature of the contract as originals, to check the location where the project is to be implemented and the infrastructure is to be executed, to identify any potential problems which may hinder sound implementation of the selected project, and give feedback to the partners etc. During the on-site visits, the JTS may recommend corrective measures.

If the on-site visits cannot be performed due to reasons imputable to the Lead Beneficiary and/or its Partners, the grant contract shall not be signed.

During the preparation of the grant contract the JTS will carry out checks to ensure the correctness of the project budget (e.g. arithmetical errors, inaccuracies and technical inconsistencies, removal of all ineligible costs and removal/reduction of costs according to the conclusions and recommendations following evaluation or recommended by the EC). Also, any clarifications or minor corrections may be made to the description of the project or to the budget in so far they do not call into question the grant award decision, do not conflict with the equal treatment of all the applicants, relate to matters clearly identified during evaluation, recommended by the EC, and/or provided by the present procedure, or are absolutely necessary for the sound implementation of the project, under the conditions and in the framework established by the Programme documents.

The checks may give rise to the requests for clarification and may lead the JTS/MA to impose modifications or corrections to address such mistakes, inaccuracies or recommendations following evaluation or recommended by the EC. The amount of the EU funding and the percentage of co-financing as a result of these corrections may not be increased. If the Lead Beneficiaries and/or their Partners do not agree/ agree only partially with the above mentioned modifications necessary for the implementation of the project in the framework established by the Programme documents, the project shall not be signed by the parties.

All partners have the obligation to provide all the necessary documents and to be available for the on-the-spot visits in order for the contracts to be signed. Please take into consideration that failure to provide the requested documents within the set deadlines during the pre-contracting period will lead to the impossibility of signing the grant contract.

The final version of the grant contract to be signed by parties shall be available during the contracting phase. By signing the grant contract, the Applicant becomes the project Lead Beneficiary and declares accepting the contractual conditions.

# ANNEXES

# Annex 1 Mandatory activities for ensuring the visibility of the project and Programme

Beneficiaries shall ensure adequate visibility of the European Union contribution to projects in order to strengthen public awareness of the European Union action and create a consistent image of the EU support in all participating countries. In this respect, they are responsible to ensure that appropriate information is communicated to the public.

Communication and visibility activities should be properly planned and budgeted at each stage of the project implementation. These activities should not only focus on publicizing the EU support for the project, but also on its outputs and results.

In order to support Beneficiaries in this endeavor, the programme will release a Communication and Visibility Manual.

The main information that must be publicized by the project relates to:

- the EU financing (programme name and EU financial instrument-European Neighborhood Instrument)

- the  total budget of project and the EU financing

- the project title

- the priority addressed by the project

- partnership

- project objectives, results and main outputs

- project duration

- project location

- target groups and the final beneficiaries

In this respect, all the projects funded by the Programme must enclose at least the following set of mandatory communication actions:

- information product (at least leaflets);

- one public event  organized by project  having minimum 20 participants which are considered relevant for the scope of the project, and with participation of local/regional media;

- at least 3 press releases timely issued in the local/regional media, informing on the milestones of the project (e.g. project start and closure, finalization of a main stage, reaching a project results etc.);

- installing temporary billboards and permanent billboards (in case of projects having an infrastructure component);

- displaying of a project roll-up  at the premises where the project is implemented and during the project events;

- stickers bearing the specific visibility elements of the programme displayed on each vehicle, equipment or other endowment purchased by the project;

- a portfolio comprising at least 10 – 15 professional photos and/or a short video (of at least 2 minutes), showing the project events and results, representative images of people participating in the project as staff and/or as beneficiaries/target group, etc) and, in case of projects with an infrastructure component, showing the situation before and after the project implementation;

- updated posts on the webpages of beneficiaries entities (project partners) or, if the case may be, on the newly created website of the project;

- at least 1 article “telling the project’s story” (of minimum 200 words and 5 photos)  available at the  Programme request.

TAKE NOTE THAT

Minimum 2% of the total direct eligible costs of the project, of the total direct eligible costs of the project, excluding costs of infrastructure/works (heading 3 in the project budget) and costs of communication and visibility actions (heading 7 in the project budget), must be allocated to  activities that ensure and the visibility of the project. Besides the mandatory activities listed above the project may envisage supplementary activities appropriate for ensuring the project visibility.

# Annex 2 State Aid self-assessment

2.1) 	Guidance for filling in the self-assessment

The State aid is not allowed for granting under the Joint Operational Programme Romania-Ukraine 2014-2020.

This self-assessment aims to provide the Applicants with the necessary instruments for developing a project in full compliance with the Programme requirements in the matter of State Aid.

Any activity of the project shall be analysed by the Applicant and partners (beneficiaries), prior to the submission of the application form. Please carefully consider each criteria so that your answers to actually reflect the reality of the project proposal. The self-assessment is part of the application and will be analysed during the evaluation process. Provided it contains State Aid elements, the project shall be rejected in entirety, except those situations when an adjustment of the activities, without affecting the project objectives, may be recommended by the Programme.

This self-assessment must refer to the project as a whole. However, when performing the State Aid self-assessment, please consider each partner and each project activity. Moreover, please take into consideration the potential ”indirect advantage”, which may occur as a result of project implementation.

An “indirect advantage” (indirect State aid) occurs when funds received by beneficiaries are channelled, during the project implementation or following the finalisation of the project, to identifiable undertakings/groups of undertakings (e.g. if the funds are used by the beneficiary for training of the employees of certain SMEs, a certain “undertaking” is going to benefit by an infrastructure developed by a beneficiary within a project, etc.). Thus, these third parties-“undertakings”- receive an advantage through the project activities that they would not have received under normal market conditions. This implies that they would be recipients of State aid.

There are 5 key questions/criteria that must be answered in order to conclude whether or not the financing of project should be considered as State Aid.

All answers YES means that financing of project shall be considered as state aid and consequently the project shouldn’t be submitted.

If at least one answer is NO, the conclusion of the self-assessment is that no State Aid is involved by the project.

2.2) 	How to interpret the criteria?

1. Are public resources involved?

The definition of state resources is aid that is granted by the state. This includes resources received by any public and private bodies to which public funds are distributed by state. State resources include funds which the State is managing. Resources coming from the EU budget are considered State resources.

This answer to this question will always be YES, because the financing source is EU funds.

2. Are public resources granted selectively to the beneficiaries?

The public resources are to be granted to beneficiaries following a selection process. Consequently, a process of selection of beneficiaries is carried out.

The answer to this question is always YES for beneficiaries selected.

3. Is any beneficiary of the project an “undertaking”?

An “undertaking” is defined as any entity, regardless of its legal status, which is engaged in an “economic activity” and its products and/or services are offered on a market. The way in which the entity is financed or its ownership  (State owned or not State owned and being a non-profit-making entity are not relevant for the purpose of this analysis, as long as for the activity performed within the project there are other commercial competitors on the market. In this respect, an “undertaking” can also be, inter alia: public universities, research institutions, voluntary organizations, an association or a sport club under the national law, NGOs or non-profit-making public organizations or even public authorities, provided that they are engaged, through the project, in an economic activity. An entity that carries out both economic and non-economic activities is to be regarded as undertaking only with regard to the economic activities.

“Economic activity” consists of offering goods or services on a given market when these activities can, at least in principle, be carried out by private actors in order to make profits (these may include e.g. training and capacity building, rental of premises, etc.).

There are not considered as “economic activity” those activities performed by a public entity when it acts “by exercising public power” or in its capacity as “public authority” and its task forms part of the essential functions of the State or is connected with those functions by its nature, its aim and the rules to which it is subject. In this respect, unless the participating countries have decided to introduce market mechanisms, there have a clear non-economic character the following activities: a) the army or the police; (b) air navigation safety and control; (c) maritime traffic control and safety; (d) anti-pollution surveillance; (e) the organisation, financing and enforcement of prison sentences; and (f) the collection of data to be used for public purposes on the basis of a statutory obligation imposed on the undertakings concerned to disclose such data.

The notion of “economic activity” is not linked to the presence of a charge. E.g. an infrastructure may qualify as being used for economic purposes even if there is no charge imposed on users. This is the case in particular if other market players offer the same or a similar service and there is thus a market for such activities. Briefly, to establish if a measure concerns an economic activity, it is relevant to assess whether there is a market for such use. The rehabilitation/construction by a beneficiary of any type of infrastructure that is meant to be exploited economically is considered an economic activity in itself.

On the other hand, “the funding of infrastructure that is not meant to be commercially exploited is in principle excluded from the application of the State aid rules. This concerns, for instance, infrastructure that is used for activities that the State normally performs in the exercise of its public powers (for instance, military facilities, air traffic control in airports, lighthouses and other equipment for the needs of general navigation including on inland waterways, flood protection and low water management in the public interest, police and customs) or that is not used for offering goods or services on a market (for instance roads made available for free public use). Such activities are not of an economic nature and consequently fall outside the scope of the State aid rules, as does, accordingly, the public funding of the related infrastructure”.When one or more activities performed by a beneficiary within the project will be considered as “economic”, this particular beneficiary will be thus considered as an “undertaking”. In case that at least one beneficiary of project is considered as an undertaking, the answer to this question should be YES.

If the activity to be performed within the project is not of an “economic” nature, the beneficiary would not be considered as an “undertaking” for State aid purposes and the answer to this question shall be NO.

4. Does any beneficiary (“undertaking) and/or a third party (“undertaking”) get an economic advantage that it could not normally get from the market?

This question is meant to analyze whether, as a result of the financing of the project, any of project beneficiaries and/or a third party (provided that any of these is an “undertaking”) would gain an advantage that under “normal market conditions” would not be gained by this particular entity, that is to say in the absence of State intervention. Therefore, an advantage (and therefore State aid) can be excluded if economic transactions carried out by public authorities are in line with normal market conditions.

An advantage can take the form of direct payment in the form of grants as well as other benefits that affect the public budget such as provision of services for free or at below-market rates (e.g. lower rents for an infrastructure, free use of an equipment or infrastructure, free training, free promotion, etc;).

Please note that the ”economic advantage” within the meaning of the State aid discipline and “profit” (e.g. as defined by  PraG, and as used by ENI CBC programmes), are different concepts.

Please note that infrastructure projects usually involve three categories of actors that are potential recipients of the State aid:  “the developer of an infrastructure (in case of this Programme - project Beneficiary), the operators (that is to say undertakings who make direct use of the infrastructure to provide services to end-users, including undertakings which acquire the infrastructure from the developer/owner to exploit it economically or which obtain a concession or lease for the use and operation of the infrastructure), and the end-users of an infrastructure, although these functions may in some cases overlap.”

a) State aid for project beneficiaries-developer of infrastructure

European Commission view on potential State Aid for beneficiaries in few examples of infrastructure:

“Public funding of research infrastructures can favour an economic activity and is hence subject to State aid rules insofar as the infrastructure is in fact intended for the performance of economic activities (such as renting out equipment or laboratories to undertakings, supplying services to undertakings or performing contract research). Public funding of research infrastructures used for non-economic activities, such as independent research for increased knowledge and better understanding, in contrast, does not fall under the State aid rules. For more detailed guidance on the distinction between economic and non-economic activities in the area of research, see the explanations provided in the Framework for State aid for research and development and innovation. “

“While roads made available for free public use are general infrastructures and their public funding does not fall under State aid rules, the operation of a toll-road constitutes in many instances an economic activity. However, the construction as such of road infrastructure, including toll-roads — as opposed to the operation of a toll-road and provided that it does not constitute dedicated infrastructure […] and its financing therefore typically does not affect trade between Member States or distort competition.[..]. The same reasoning applies to investments in bridges, tunnels and inland waterways (for example, rivers and canals)”.

b) State aid for operators

In case the Beneficiary developer make the infrastructure available to an operator who in turn provides services to end-users of the infrastructure, must be ensured that operator will not receive an advantage if the use of the infrastructure provides it with an economic benefit that it would not have obtained under normal market conditions. This normally applies if what the operator pay for the right to exploit the infrastructure is less than what it would pay for a comparable infrastructure under normal market conditions. An economic advantage to the operator can in particular be excluded if the concession to operate the infrastructure (or parts of it) is granted through an open, transparent and unconditional tender and the operator pays to the Beneficiary -developer, for the use of the infrastructure, a fee/royalty set up at a value at least equal with the amortization of the infrastructure (namely proportionally with the value of the infrastructure and its use time).

c) State aid to end-users

An advantage to end-users can be excluded where the fees for use of the infrastructure have been set through an open, transparent and unconditional tender.

If there is granted an “economic advantage” to a beneficiary (“undertaking”) and/or a third party -operator or end-user, (“undertaking”), the answer to this question is YES.

If no economic advantage is granted to any beneficiary (“undertaking”) and/or to a third party (“undertaking”), the answer to this question is NO.

5. Does the aid (financing of project) distorts or threatens to distort competition and trade between Member States, and/or between Member States and participant countries?

A measure granted by the State (including EU funds) is considered to distort or threaten to distort competition and trade when this measure is able to improve the competitive position of the recipient compared to other undertaking(s) with which enter in competition.

This question should refer both to beneficiaries (“undertakings”) and third parties (“undertakings”) that benefit as a result of project implementation.

Please note that provided that the service or products financed are of a merely local interest, the trade between the EU Member States or between Member States and a specific CBC Partner Country is not going to be affected. In order to assess that, the beneficiaries have to demonstrate that:

- the aid does not create obstacles to the establishment of undertakings from other Member States, the aid does not lead to investments being attracted in the region concerned;

- the goods or services produced under the project are purely local or have a geographically limited attraction zone;

- there is at most marginal effect on the markets and, in particular, on consumers in neighbouring Member States/ participating countries.

- The market share of the beneficiary is limited.

The Commission considered, in a number of decisions, in the light of the specific circumstances of each case, that public support was not liable to affect trade between Member States. Examples of such cases, that may be relevant for the Programme, are:

a) sports and leisure facilities serving predominantly a local audience and unlikely to attract customers or investment from other Member States;

b) cultural events and entities performing economic activities which however are unlikely to attract users or visitors away from similar offers in other Member States. The Commission considers that only funding granted to large and renowned cultural institutions and events in a Member State which are widely promoted outside their home region has the potential to affect trade between Member States;

c) hospitals and other health care facilities providing the usual range of medical services aimed at a local population and unlikely to attract customers or investment from other Member States;

d) news media and/or cultural products which, for linguistic and geographical reasons, have a locally restricted audience;

e) a conference centre, where its location and the potential effect of the aid on prices is genuinely unlikely to divert users from other centres in other Member States;

f) an information and networking platform to directly address problems of unemployment and social conflicts in a predefined and very small local area;

g) small ports that predominately serve local users, thereby limiting competition for the services offered to a local level, and for which the impact on cross-border investment is genuinely no more than marginal;

h) the financing of certain cable ways (and in particular ski lifts) in areas with few facilities and limited tourism capability. The Commission has clarified that the following factors are typically taken into account to draw a distinction between installations supporting an activity capable of attracting non-local users, which are generally considered to have an effect on trade, and sport-related installations in areas with few facilities and limited tourism capability, where public support may not have an effect on trade between Member States: (294) a) the location of the installation (for example within cities or linking villages); b) operating time; c) predominantly local users (proportion of daily as opposed to weekly passes); d) the total number and capacity of installations relative to the number of resident users; e) other tourism-related facilities in the area. Similar factors could, with the necessary adjustments, also be relevant for other types of facilities.

If cannot be demonstrated that project does not distorts the competition and trade at the level of beneficiary (“undertaking”) or at the level of third parties(“undertaking”) , the answer to this question will be YES

If the project can demonstrate that both at the level of beneficiary (“undertaking”) and/or at the level of third parties (“undertaking”), the competition is not going to be distorted, the answer to this question will be NO

2.3) 	Self-Assessment grid

|  | Key questions | Answers |
| --- | --- | --- |
| 1. | Are public resources involved? | Yes X No □ |
| 2. | Are public resources granted selectively to the beneficiaries? | Yes X No □ |
| 3. | Is any beneficiary of the project an 'undertaking'? | Yes □ No □ In case of YES, list the “economic activities” of the partner concerned. Analyse the possibility of excluding these “economic activities” from the project. |
| 4. | Does any beneficiary (“undertaking”) and/or a third party (“undertaking”) get an “economic advantage” that it could not normally get from the market? | Yes □ No □ In case of YES, identify the list of activities linked to the “economic advantages”. Analyse the possibility of excluding these activities from the project. |
| 5. | Does the aid (financing of project) distorts or threatens to distort competition and trade between Member States, and/or between Member States and participant countries? | Yes □ No □ In case of YES, identify the list of activities that may conduct to a distortion of competition and trade. Analyse the possibility of excluding these activities from the project. |

As a result of the self-assessment, please conclude if financing your project can be considered as State Aid. Please note that all beneficiaries must ensure that they comply with state aid rules towards end users. If possible, adjust the project by reconsidering those activities that put the financing the project in the State Aid category. We remind you that all answer YES indicates the existence of State Aid.

| Name: |  |
| --- | --- |
| Organisation: |  |
| Position: |  |
| Signature and stamp: |  |
| Date and place: |  |

# Annex 3 Job description (template)

| Project title |  |
| --- | --- |
| Organisation |  |

Job description

| Job Name |  |
| --- | --- |
| Job Level | executive / managerial |
| Main purpose |  |
| Specific conditions for the job |  |
| Studies required for the job |  |
| Training |  |
| Computer skills |  |
| Languages |  |
| Working experience |  |
| Skills required |  |
| Specific requirements |  |
| Responsibilities |  |

Acknowledged,                                                                                                                  Approved,

# Annex 4 Declaration and statements (templates)

# 4.1 Declaration by the Applicant

The Applicant, [name of the organization - in English and in national language], represented by the undersigned, being the authorized signatory of the Applicant, hereby declares that:

- It has the sources of financing and the professional competence and qualifications required to implement the project, as described in the application form.

- Undertakes to comply with the all obligations that are in line with the principles of good partnership.

- Is directly responsible for the preparation, management and implementation of the project together with its Partners, and is not acting as an intermediary.

- The activities that will be carried out in the project are in line with the European Communities’ and the national legislation and policies, and with the rules of the Programme in particular, are compliant with state aid regulations/ agreements and gratuitousness of project results.

- Is not in any of the situations excluding them from participating in contracts which are listed in Article 106 (1) of Regulation (EU, Euratom) no. 966/ 2012. Furthermore, it is recognised and accepted that if it will participate in spite of being in any of these situations, it may be excluded from other procedures in accordance with Article 107 of Regulation (EU, Euratom) no. 966/ 2012.

- Is eligible in accordance with the criteria set out in the Procedure for the evaluation and approval of large infrastructure projects selected through direct award.

- If recommended to be awarded a grant, it accepts the contractual conditions as laid down in the grant contract.

- [only for Ukrainian organizations] Is able to open a dedicated bank account in a state-owned bank from Ukraine and to transfer/ receive funds to/ from foreign countries.

- Is aware that, for the purposes of safeguarding the financial interests of the EU, the personal data may be transferred to internal audit services, to the European Court of Auditors, to the Financial Irregularities Panel or to the European Anti-Fraud Office.

- The following proposals have been submitted (or are about to be submitted) to the European Institutions, the European Development Fund and the EU Member States in the last 12 months:

[list only projects in the same field as this proposal]

[Tick-mark each statement]

The Applicant is fully aware of the obligation to inform without delay the Managing Authority to which this project proposal is submitted if the same proposal for funding made to other European Commission departments or European Union institutions has been approved by them after the submission of this application.

The Applicant is aware that the partnership is a relationship of substance involving shared responsibilities in undertaking the project to be funded by the Joint Operational Programme Romania – Ukraine 2014 - 2020. In this respect, the principles of good partnership practice set out below are acknowledged and agreed and, as Applicant, I hereby state that:

- I understood what the role in the project will be.

- I am designated and authorized by the project Partners to represent them in all dealings with the Managing Authority and further on, to sign the contract with the Managing Authority and to represent them during project implementation.

- I shall consult with the project Partners regularly and keep them fully informed of the progress of the project.

- I will forward copies of the reports made to the Managing Authority to the project Partners.

- Proposals for substantial changes to the action (e.g. activities, partners, etc.) will be previously agreed with all the project Partners before being submitted to the Managing Authority.

- I will agree before the end of the project, on an equitable distribution of equipment, vehicles and supplies purchased with the EU grant among local partners or the final beneficiaries, if the case may be.

- I am aware of the obligation to sign the Partnership Agreement stating the tasks and obligations in the project, before the signature of the grant contract with the Managing Authority.

[Tick-mark each statement if applicable, and delete those that are not applicable]

The Applicant is not entitled to recover any paid VAT (Value Added Tax) by whatever means, and therefore all project related expenditure to be reported will include VAT.

The Applicant is entitled to recover any paid VAT (Value Added Tax), and therefore all project related expenditure to be reported will not include VAT.

The Applicant is entitled to partially recover the paid VAT (Value Added Tax), and therefore the respective project related expenditure to be reported will not include VAT. For the partially non-recoverable paid VAT (Value Added Tax) by whatever means, the respective Action related expenditure to be reported will include VAT.

[only for Ukrainian organizations] Once the grant contract is signed and before requesting the first pre-financing, the Applicant will seek for registration at the Ministry of Economy and Trade in Ukraine.

It is hereby certified that the [name of the organization - in English and in national language] commits itself to the project and intends to provide and spend EUR [insert amount] as (national) co-financing to the project during its implementation, as well as any ineligible expenditure or any other cost related to the project implementation. This commitment is backed by the decision of the empowered bodies, available at request.

It is hereby confirmed that no expenditure related to the activities foreseen to be implemented in the above mentioned project by [name of the organization - in English and in national language] has been or will be funded by any other EU programme.

On behalf of the Applicant

| Name |  |
| --- | --- |
| Signature and stamp |  |
| Organisation |  |
| Position |  |
| Date and place |  |

# 4.2 Partnership Statement

A Partnership is a relationship of substance involving shared responsibilities in undertaking the project to be funded by the Joint Operational Programme Romania – Ukraine 2014 - 2020.

The Partner, [name of the organization - in English and in national language], represented by the undersigned, being the authorised signatory, hereby declares that principles of good partnership will be followed and also that:

- Has read the project proposal and understood what our role in the project will be before the project proposal is submitted for evaluation.

- Got acquainted with the Joint Operational Programme Romania-Ukraine 2014-2020 and the Procedure for the evaluation and approval of large infrastructure projects selected through direct award.

- Is not in any of the situations excluding them from participating in contracts which are listed in Article 106 (1) of Regulation (EU, Euratom) no. 966/ 2012. Furthermore, it is recognised and accepted that if it will participate in spite of being in any of these situations, it may be excluded from other procedures in accordance with Article 107 of Regulation (EU, Euratom) no. 966/ 2012.

- We designate and authorise the Applicant [insert the name of the applicant - in English and in national language] represent us in all dealings with the Managing Authority and further on, to sign the contract with the Managing Authority and represent us during project implementation.

- It has the sources of financing and the professional competence and qualifications required to implement its share of project activities, as described in the application form.

- The activities that will be carried out in the project are in line with the European Communities’ and the national legislation and policies, and with the rules of the Programme, in particular, they are compliant with state aid regulations/ agreements and gratuitousness of project results.

- Is aware of the Applicant’s obligation to consult our organisation and other Partners regularly and keep us fully informed of the progress of the project implementation.

- [only for Ukrainian organizations] Is able to open a dedicated bank account in a state-owned bank and to transfer/ receive funds to/ from foreign countries.

- Have agreed with the Applicant that he is obliged to send us copies of the reports made to the Managing Authority.

- Is aware that proposals for substantial changes to the project (e.g. activities, Partners, etc.) should be agreed by the Partners before being submitted to the Managing Authority.

- Is aware that before the end of the project, the Partners must agree on an equitable distribution of equipment, vehicles and supplies for the project purchased with the EU grant among local Partners or the final beneficiaries of the project.

- Is aware of our obligation to sign a Partnership Agreement specifying the Partners’ tasks and obligations in the project, before the Applicant is signing the grant contract with the Managing Authority.

- Will keep available all documents related to the project in accordance with the programme requirements on the availability of documents.

- Will assume responsibility in the event of any irregularity in its own declared expenditures, and will repay the Applicant the amounts unduly received/ paid.

- Will inform the public about European Communities’ assistance received from the Programme to implement the project in compliance with the visibility rules of the Joint Operational Programme Romania- Ukraine 2014-2020.

[Tick-mark each statement if applicable, and delete those that are not applicable]

Our organisation is not entitled to recover any paid VAT (Value Added Tax) by whatever means, and therefore all project related expenditure to be reported will include VAT.

Our organisation is entitled to recover any paid VAT (Value Added Tax), and therefore all project related expenditure to be reported will not include VAT.

Our organisation is entitled to partially recover the paid VAT (Value Added Tax), and therefore the respective project related expenditure to be reported will not include VAT. For the partially non-recoverable paid VAT (Value Added Tax) by whatever means, the respective project related expenditure to be reported will include VAT.

[only for Ukrainian organizations] Once the grant contract is signed, our organisation will seek for registration at the Ministry of Economy and Trade in Ukraine.

It is hereby certified that the [name of the organization – in English and in national language] commits itself to the project and intends to provide and spend EUR [insert amount] as (national) co-financing to the project during its implementation, as well as any ineligible expenditure or any other costs related to the project implementation. This commitment is backed by the decision of the empowered bodies, available at request.

It is hereby confirmed that no expenditure related to the activities foreseen to be implemented in the above mentioned project by [name of the organization - in English and in national language] has been or will be funded by any other sources including other EU programmes.

Signed on behalf of the Partner [name of the organization – in English and in national language]:

| Name: |  |
| --- | --- |
| Organisation: |  |
| Position: |  |
| Signature and stamp: |  |
| Date and place: |  |

Article 2, Commission Implementing Regulation (EU) No.897/2014 of 18 August 2014 laying down specific provisions for the implementation of cross-border cooperation programmes financed under Regulation (EU) No 232/2014 of the European Parliament and the Council establishing a European Neighborhood Instrument

According to the clarifications provided by EC and compiled by TESIM

Exception to this requirement is made only when the respective Partner is the owner of the location (land/building/space)

For the full list of indicative activities, for each Thematic Objective / Priority eligible under the selection process please consult the Joint Operational Programme

The project summaries will be submitted for the JMC approval depending on their readiness

The full project application package will be submitted for the JMC approval depending on their readiness

Unless the EC requests additional information

Some of the sections shall be further developed in the Application Form.

Special attention should be given to article 39.3 of ENI CBC IR: “Any project including an infrastructure component shall repay the Union contribution if, within five years of the project closure of within the period of time set out in state aid rules, if applicable, it is subject to a substantial change affecting its nature, objectives and implementation conditions which would result in undermining its original objectives. Sums unduly paid in respect of the project shall be recovered by the Managing Authority in proportion to the period for which the requirement has not been filled”.

The project budget shall be developed in full compliance with the detailed description of infrastructure (presented at group of activities GA#4 Infrastructure within the Application Form), with due attention to the real market prices of supplies, services and works involved. Nevertheless, the budget for the infrastructure needs to be detailed in the excel sheet Infrastructure budget breakdown to be annexed to the Application Form.

Group of activities 4, Works/ Infrastructure

The capacity building component should be understood as a soft component.

According to art.43(2) of the IR, and the clarifications provided by EC and compiled by TESIM

According to art.43(2) of the IR, and the clarifications provided by EC and compiled by TESIM

According to art.43(2) of the IR, and the clarifications provided by EC and compiled by TESIM

According to art.43(2) of the IR, and the clarifications provided by EC and compiled by TESIM

As clarified by the EC, in case the feasibility study has been outsourced, it is considered that, by default, an independent quality review has been given whereas, in case of an "in-house" feasibility study development exercise, an external expert needs to be contracted to verify the contents of the document.

E.g. government decision, law, government ordinance, decision of local authorities, property act, etc

For locations where equipment under 60,000 EUR is to be installed/used or the infrastructure component is under 1 million euro, none of the documents listed at (a) to (c) are required

The statement should be given by the owner of the land/ building/ space

E.g. government decision, law, government ordinance, decision of local authorities, property act, etc.

For locations where equipment under 60,000 EUR is to be installed/used, none of the documents listed at (g.1) to (g.3) are required.

The statement should be given by the owner of the land/ building/space

COMMISSION IMPLEMENTING REGULATION (EU) No 897/2014 laying down specific provisions for the implementation of cross-border cooperation programmes financed under Regulation (EU) No 232/2014 of the European Parliament and the Council establishing a European Neighborhood Instrument

According to Commission Notice on the notion of State aid as referred to in Article 107(1) of the Treaty on the Functioning of the European Union, (2016/C 262/01)

According to Commission Notice on the notion of State aid as referred to in Article 107(1) of the Treaty on the Functioning of the European Union, (2016/C 262/01)

According to Commission Notice on the notion of State aid as referred to in Article 107(1) of the Treaty on the Functioning of the European Union, (2016/C 262/01)

According to Commission Notice on the notion of State aid as referred to in Article 107(1) of the Treaty on the Functioning of the European Union, (2016/C 262/01)

Legal representative of the organization. In the case in which is  not signed by the legal representative, a mandate of delegation from the legal representative is to be attached.

Legal representative of the organization. In case the Declaration by the Applicant is not signed by the legal representative, a mandate of delegation from the legal representative is to be attached to the Declaration by the Applicant.

Legal representative of the organization. In case the Partnership Statement is not signed by the legal representative, a mandate of delegation from the legal representative is to be attached to the Partnership Statement.