## Slide 1: Pre-requisites for project launching
TESIM Capacity building events for RO-UA applicants
13th / 16th March 2018
Chernivtsi / Odessa, Ukraine
Notes: During the intro to the session, a clarification on the terminology needs to be provided: lead applicant and project partner are terms used “before the grant contract”, whereas the lead beneficiary and the beneficiaries are the ones implementing the approved project after the grant contract is signed.

## Slide 2
Building a partnership
Setting up the project team
Establishing internal communication channels
Effective communication plan
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 3: Why a partnership?
Notes: Before entering into the contents of the presentation, the participants are asked to share their ideas about the necessity to implement the projects in partnership. Additional clarifying questions that the expert can ask are: “What are the benefits of implementing a project together with the other partners?” or “Why are the partners needed in a project?”

## Slide 4
Partnership is a requirement
It is a legal requirement for a project
  at least one partner registered in Romania
  at least one partner registered in Ukraine
  BUT PARTNERSHIP IS MORE THAN A MERE REQUIREMENT!
Project benefits from the joint work:
      addressing joint challenges / solving common problems
      exploiting joint opportunities / looking for common solutions
      exchanging and learning from each other
Notes: This slide stresses that even if partnership is a requirement that comes directly from the legal framework and not fulfilling this requirement will result into a non-eligible application, there are also practical benefits of working together in a project.

## Slide 5
Project partnership
Opportunities / challenges of working together
Previous experience
Language
Working style
Different structures
Decision-making process
Culture
Belief systems
Rules and procedures
Notes: Depending on the time available, this can be either an individual reflection of each participant, where they are asked to define for themselves what they consider a challenge and what – an opportunity and add their own ideas to the list. Time allowing, the same can be done as a group discussion. Aim of this exercise is to show that there are many aspects that need to be taken into accout when working together.

## Slide 6: OK, I need partners. But where and how to find them?

## Slide 7
Partner search
Define the thematic profile of the partner
Define type of institution that is needed
Ask your partners, programme bodies, umbrella organisations, other players in the relevant sector
Do your own search
Connect and promote your project idea!
Notes: The possible criteria that can be used when looking for the project partners – experience, legal status, expertise, previous cooperation, influence, relevance, financial capabilities, reputation. This can be asked to the participants!
A special mention respective organization has the necessary operational and financial capacity to implement the selected projects.

## Slide 8
Partner search tools
Data of the previous ENPI CBC programme - partners of the implemented projects at http://www.ro-ua-md.net/projects/awarded-projects/ (and other programmes with participation of Romania / Ukraine).
International database www.keep.eu on various cross border cooperation projects, including ENPI / ENI.

## Slide 9
Promoting the project idea
Looking for a partner is like a business negotiation!
You have to understand your partner’s needs and perspectives, and communicate your own ones in that context!
Mutual understanding -> win-win!
Listen to your partner needs!
Notes: “The partners operate on an arena of needs. Both approach these needs from their own points of view. You have to understand your partner’s needs and perspectives, and communicate your own ones in that context.

## Slide 10: I have found partners. But is it enough?

## Slide 11
Evaluate your partnership
Who else is working in ‘the field’? Should they be involved?
Who can best promote the project ideas, bring them to the decision-makers? Are they in?
Are the project partners able to convey the messages to the wider public? Will you need a hand in communication activities?
Does the project target group have an organised representation (NGO, council, etc.)? Shall they be involved?
Do the project partners have all competences needed to implement the project? Is everyone you need on board?

## Slide 12: Working together

## Slide 13
Keys to project management
Project manager
Technical team
Finance, accounting & legal team
Comm. & cap. team
MA/JTS
Project partners (beneficiaries)
Partners’ technicians /External experts/Target groups work plan
Target groups comm. & cap. plan
Notes: 13

## Slide 14
Keys to project management
Comm & cap team
Implementation team
Financial team
Partners’ Committee
Project manager
(Lead beneficiary )
Financial manager
(Lead beneficiary)
Implementation manager
(Lead Beneficiary)
Comm & cap manager
(Lead beneficiary)
Financial managers
(Partners)
Comm & cap technicians
(Partners)
Technicians
(Lead Beneficiary & partners)
Extern support to management & auditors
No pre-defined way! In smaller projects, one person can be responsible for several functions!
External support to comm & cap
External support to implementation
Notes: 14

## Slide 15
Lead partner principle
How does it translate into practice?
Project partners (beneficiaries)
actively cooperate in the development and implementation of projects
cooperate in the staffing and/or financing of projects
are legally and financially responsible for the activities that they are implementing and for the share of the funds that they receive
Applicant (lead beneficiary)
is representing the entire project partnership
is legally acting on behalf of the partnership (e.g. submitting the application, signing the grant contract, submitting project reports, requesting and receiving project payments)
Notes: The lead partner principle is introduced, as a principle for implementation of the CBC projects. The supporting material for this slide is the handout on tasks and responsibilities of the LB and the beneficiaries – it explains in more detail the additional tasks that the applicant/ lead beneficiary has to undertake during development and implementation of the project

## Slide 16
Documents regulating relations
MANAGING AUTHORITY OF THE PROGRAMME
Grant Contract
APPLICANT
PARTNER
PARTNER
Partnership Agreement
Notes: This scheme refers to the legal documents that regulate implementation of the project

## Slide 17
Wrap up: key messages
Be active: use different tools for partner search within and outside the Programme
Be careful: check the experience, expertise and capacity of your potential partners
Be balanced: distribute tasks and responsibilities to all partners based on their experience and capacities
Be patient: you’ll need to brainstorm, exchange and learn to make your project a success
Notes: The lead partner principle is introduced, as a principle for implementation of the CBC projects. The supporting material for this slide is the handout on tasks and responsibilities of the LB and the beneficiaries – it explains in more detail the additional tasks that the applicant/ lead beneficiary has to undertake during development and implementation of the project

## Slide 18: Communication

## Slide 19
Why a communication strategy for a CBC project? Because…
…..You need to inform the wide audience at EU and local level
…It’s a formal requirement but don’t consider it as a separate additional activity.
You must persaude your target groups to change their behaviour
…It’much more than a logo or a project website: you have a story to tell
.. You have to engage the right stakeholders to increase the project ownership
Communication it’s a strategic tool for a successful project implementation

## Slide 20
Developing your communication strategy
Communication objectives
Main target groups
Main messages for the target groups identified
Main communication activities for the year ahead
What activities can support capitalisation?
Evaluation of communication to amend next plan
In the Application form, you must describe, plan, quantify and allocate resources for communication activities
Be aware of the requirements set up at EC and programme level in terms of visibility guidelines and communication plans
Notes: Evaluation of the communication plan towards the end of the year will give insights into what activities work, what messages are being passed to the target groups etc. The results of this will help to defiine what changes are needed for the following communication plan.

## Slide 21
Key elements of communication matrix
Key elements | Why/What/When/Whom | How
Communication objectives | Why I need to communicate? | Objectives must be Interrelated with the project operational objectives; must be clear, specific and measurable
Main target groups | By whom my messages should be understood? | Involved in decision-making process/in project implementation/Influencing policy implementation/Policy end-users
Key Messages | What do you want to communicate: | Each project should have 2-3 key messages which are short simple and give a clear idea of what it is about. .
Timing and responsibilities | When: take into account project work plan | Check project results/outputs availability before planning comm activities) and allocate different level of responsibilities among the partners
Evaluate: which indicators? | Did you reach the target group by conveying the right message? Did they understand it? | Don’t forget to set up indicators (qualitative and quantitative) in order to measures the achieved results.
Notes: Key messages :
1)be careful , don’t forget you need first to identify your problems and think about expected change in terms of communication and only after define your activities”
2) you’ll need to work in close cooperation with the project manager as the communication plan must be developed in parallel with the project logframe (what we have to communicate, when?etcc)
3) Target groups include both internal (organisations implementing the project) and external (end-users, general public, different stakeholders, regional authorities, the managing authority) groups. Who could be interested in the project?/Who should know about the project (even if they are not that interested)? /Who would you like to know about the project?
3) Indicators : describe the indicators used for verifying the success of the communication activities. You can count for example the project’s media visibility, followers on social media, people contacted in events etc. More ambitious indicators can relate to for example change of attitude, increased knowledge etc. but in these cases you need to have a baseline value in order to follow the progress.

## Slide 22
Activities/Tools
Check if the programme provides a website layout, domain and hosting for the projects !
Notes: Possible : project website, events, networking, social media, traditional media, photos and videos, publications, promotional materials newsletters etcc
Project tools must be complementary with the programme communication tools and contribute to progrogramme comm strategy.

## Slide 23
Social media
low-cost, interactive, fast, real time information and interaction, an increase of traffic to our website, good possibility of linking and networking with relevant actors;
Define which target groups you want to reach through the social media? Which media is the best for the target group?
The information provided has to be accurate and updated; you still need resources to use the chosen channels.
Make sure you inform the Managing Authority on all the social media you are using. The Programme will follow you and share your content forward.
It is also advisable to connect with other projects and network with different stakeholders and target groups. In Twitter you can use the programme hashtag

## Slide 24
Media relation : press release
Write a capturing headline
Use easy language and keep the release short;
Tell a story: give a face to the story and tell the journalist what the story means to their audience (for example: tell about a person whose life has been impacted by the project);
Remember to mention the financiers and required visibility elements to the press release;

## Slide 25
Set up a project communication team
Drafting and implementing the communication plan
Communicating with the JTS and double checking the programme requirements
Coordinating all communication activities among all Project Beneficiaries in close coordination with the project manager;
Building the capacity of Project Beneficiaries to communicate project achievements effectively;
Possible tools : joint calendars, online collaboration platforms for file sharing and online storage of files; Shared project ideas database

## Slide 26
Internal communication strategy to be set up for…
ensuring that the partners have the same level of information
developing ownership of project contents and results
monitoring the project performance
knowing the responsibilities and tasks of each partner

## Slide 27
Key messages
Be careful : communication goes beyond the visibility requirement
Be a storyteller: your project has its own story to be told to the external stakeholders
Be innovative: use the social media to keep informed your target groups
Stay focused: in all your communication outputs the Cross border impact must be there

## Slide 28: Go for a successful ENI CBC partnership!