## Slide 1: WORK WITH THE APPLICATION FORM STEP BY STEP

## Slide 2: WORK PLAN PER GROUP OF ACTIVITIES (GAs)
Information must be consistent within different parts of the Application Form (Logical Framework, Work plan, Budget), annexes and the supporting documents must be the same.
Follow closely the instructions and give all the information required. E.g. responsible partner, related project result, deliverables
Give a chronological order to project activities. Give an appropriate timeframe to carry out each of them (not too long and not too short).
Take note that certain project activities may run in parallel.
Project Main Outputs are mandatory to achieve the Results. All the others are project Deliverables.

## Slide 3: WORK PLAN PER GROUP OF ACTIVITIES (GAs)
MANDATORY WORK PACKAGES
*Capacity building activities are mandatory for HARD projects
Note that
In case requirements are not met, the project may be rejected.
HARD projects | SOFT projects
GA 0 - Project preparation | GA 0 - Project preparation
GA 1 - Project management | GA 1 - Project management
GA 2 - Information and communication | GA 2 - Information and communication
GA 3 – Specific activities* | GA 3 – Specific activities
GA 4 – Infrastructure* | GA 4 – Infrastructure POSSIBLE but NOT MANDATORY

## Slide 4: WORK PLAN PER GROUP OF ACTIVITIES - GA 0 Project preparation
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to
Project preparation
1.1 (d) Cross cutting themes
2.2 (c) Partners’ contribution to the project
3.1 (a) Project preparedness
3.1 (c) Project planning & methodology
 TIPS

## Slide 5: WORK PLAN PER GROUP OF ACTIVITIES - GA 1 Project management (1/2)
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to project management
1.1 (d) Cross cutting themes
2.2 (c) Partners’ contribution to the project
3.1 (b) Project management
3.1 (c) Project planning & methodology

## Slide 6: WORK PLAN PER GROUP OF ACTIVITIES - GA 1 Project management (2/2)
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to project management
1.1 (d) Cross cutting themes
2.2 (c) Partners’ contribution to the project
3.1 (b) Project management
3.1 (c) Project planning & methodology

## Slide 7: WORK PLAN PER GROUP OF ACTIVITIES - GA 2 Information and communication plan
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to information and communication plan
1.1 (d) Cross cutting themes
2.2 (c) Partners’ contribution to the project
3.1 (b) Project management
3.1 (c) Project planning & methodology
Annex H.3 - Inventory of minimum mandatory communication promotion information activities

## Slide 8: WORK PLAN PER GROUP OF ACTIVITIES - GA 3 Project specific (1/2)
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to other project activities
1.1 (d) Cross cutting themes
2.2 (c) Partners’ contribution to the project
3.1 (c) Project planning & methodology
Notes: .

## Slide 9: WORK PLAN PER GROUP OF ACTIVITIES - GA 3 Project specific (2/2)
Relates to other activities, specific for the project

## Slide 10: WORK PLAN PER GROUP OF ACTIVITIES - GA 4 Infrastructure (1/3)
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to the infrastructure
2.2 (c) Partners’ contribution to the project
3.1 (a) Project preparedness
3.3 (c) Description of the infrastructure component
3.3 (e) Financial feasibility of the infrastructure component

## Slide 11: WORK PLAN PER GROUP OF ACTIVITIES - GA 4 Infrastructure (2/3)
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to the infrastructure
3.3 (d) Technical feasibility of the infrastructure component

## Slide 12: WORK PLAN PER GROUP OF ACTIVITIES - GA 4 Infrastructure (3/3)
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to the infrastructure
3.3 (d) Technical feasibility of the infrastructure component

## Slide 13: PROJECT DESCRIPTION - C.5 Capacity building activities
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to capacity building
3.1 (a) Project preparedness
3.3 (d) Technical feasibility of the infrastructure component

## Slide 14: PROJECT DESCRIPTION - C.6 Flexibility rule
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to flexibility requirements
2.2 (a) Relevance of the project partnership
3.1 (c) Project planning & methodology

## Slide 15: PROJECT DESCRIPTION - C.7 Indicative time plan
Groups of activities
Activities
Deliverables
The project indicative time plan (Gantt chart) is an important implementation tool.
Notes: Activitatea 1.2 nu are date – interval de timp, deliverable, pentru ca a fost introdusa, dar nu au fost completate date.

## Slide 16: PROJECT DESCRIPTION - C.8 Sustainability (1/2)
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to project sustainability
1.1 (d) Cross cutting themes
3.4 (a) Sustainability of project Outputs and Results

## Slide 17: PROJECT DESCRIPTION - C.8 Sustainability (2/2)
Any project including an infrastructure component shall repay the Union contribution if, within five years of the project closure or within the period of time set out in state aid rules, where applicable, it is subject to a substantial change affecting its nature, objectives or implementation conditions which would result in undermining its original.
(Art. 39, point 3 from 897/2014 IR)

## Slide 18: PROJECT DESCRIPTION - C.9 Cross cutting themes
Check Evaluation Grid for Step 2 (technical and financial evaluation) for criteria making reference to the cross cutting themes
1.1 (d) Cross cutting themes
Positive influence on more than one cross cutting theme of the Programme, to bring the project better scores

## Slide 19
Thank you for attention!
Please check regularly for updates on the Programme website at
http://www.ro-ua.net/en/
Joint Technical Secretariat
Regional Office for Cross-border Cooperation for Romania – Ukraine border
8A, Bistritei street, 720274 Suceava, Romania
info.ro-ua@brctsuceava.ro