## Slide 1: Project management and legal requirements affecting project delivery
TESIM Capacity building events for RO-UA applicants
13th / 16th March 2018
Chernivtsi / Odessa, Ukraine

## Slide 2
Good internal monitoring
Project risk management
Setting up the internal control system
Legal requirements affecting project delivery
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 3: Internal project monitoring
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 4
Levels of project monitoring
Internal project monitoring
Effective decision making by the project managers
Accountability for the use of resources and achievement of results
Monitoring by the MA/JTS
Ensures appropriate grant contract management
Allows the programme bodies to follow the implementation of the project
ROM under responsibility of the MA
Independent assessment of the project performance/results
Identify successes and risks for the use of stakeholders

## Slide 5
Why to have good internal monitoring?
Good monitoring allows to timely identify set-backs/delays or opportunities.
Good monitoring allows to assess the progress towards project results.
Good internal monitoring leads to reliable reporting to the programme authorities.
Reliable reports tend to have less clarifications from the programme authorities!

## Slide 6
How to build good internal monitoring?
Continuously monitor project progress
Conduct team reviews
Timely address potential project modifications
Communicate
Submit the reports

## Slide 7
How to build good internal monitoring?
Responsibilities | Lead beneficiary | Beneficiaries
Continuously monitor project progress | Monitor progress of key project elements | Review progress of tasks on beneficiary level
 | Deliverables comply with content and quality requirements | Report to the LP / inform about progress
 | Milestones and schedule is followed | Inform of the potential risks or problems
 | Costs as budgeted, payments and receipts as in financial plan | Costs as budgeted at individual level

## Slide 8
How to build good internal monitoring?
Responsibilities | Lead beneficiary | Beneficiaries
Conduct team reviews | Determine the information needs in the partnership | Inform about information needs and discuss them with the LP and the rest of the partnership
 | Decide/ discuss how best to communicate information both internally and externally | Regularly exchange status information

## Slide 9
How to build good internal monitoring?
Responsibilities | Lead beneficiary | Beneficiaries
Timely address potential project modifications | Document and prioritise the possible modifications requested | Outline the modification – link it to the original plan – highlight deviations
 | Internally assess the potential modifications against the programme rules | Estimate the impact of the modification on the partner’s part and on the project
 | Inform programme management, or make a request for a modification | Inform and discuss with the LP and the rest of the partnership
 | Provide a description of how the modification requested affects the project resources and outcomes | 
 | If relevant, ensure the approved modifications are incorporated in the project structure | 

## Slide 10
How to build good internal monitoring?
Responsibilities | Lead beneficiary | Beneficiaries
Communicate | Harmonise key messages used for communication | Prepare and present deliveries and achievements as requested
 | Prepare information and material to be used for communication | Communicate project achievements in their networks
 | Communicate project achievements in their networks | 

## Slide 11
How to build good internal monitoring?
Responsibilities | Lead beneficiary | Beneficiaries
Formal project progress review | Identify what needs to be prepared for the report | Undertake progress review (e.g. against timetables, indicators, etc.)
 | Allocate tasks in the partnership regarding the provision of information | Prepare and present status information as requested
 | Undertake overall project progress review (e.g., against timetables, indicators, etc.) | Identify action items that require attention by management and/or stakeholders
 | Prepare the project periodic reporting and submit to the programme | 

## Slide 12
How to build good internal monitoring?
Good internal monitoring goes well beyond interim / final reporting!
Notes: For the presentation: to emphasise that regular internal ‘reports’ at short intervals can be an effective (3-6 months maximum) for ongoing monitoring, while reporting to JTS may be only once per year.

## Slide 13: Project risk management
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 14
Risks in the project
Risk is any event or issue that could occur and adversely impact the achievement of the project objectives.

## Slide 15
Risks in the project
Type of objective | Examples of objectives
Operational/Strategic | Ensure achievement of project objectives/results/indicators/outputs Implement the work plan according to the schedule
Reporting | Follow programme reporting requirements Establish internal monitoring
Compliance | Ensure eligibility of costs Assess the necessity for project changes
When discussing possible risks with partners, always relate them to your objectives!
Notes: NOTE N°1: TITLES OF SLIDES ARE WRITTEN USING CENTURY GOTHIC 24, TESIM PURPLE COLOUR, NOT IN CAPITALS. TEXT IS JUSTIFIED LEFT AND ALIGNED WITH END OF LINE BELOW.
NOTE N°2: HEADINGS ARE WRITTEN IN CAPITALS IN BOLD TESIM BLUE, CENTURY GOTHIC 24. THEY ARE CENTRED AND NOT UNDERLINED

## Slide 16
Risks in the project
If the project objectives are clear, what could possibly go wrong?
Cost risks
Is it possible that the project costs more than budgeted, affecting delivery of results? How big is the currency fluctuation risk?
Schedule risks
What are the chances to have serious delays in implementing the activities?
Procurement / contractual risks
Financial risks
Political risks
Staff risks
Can we expect to complete procurements in time and successfully?
Can we and our partners expect cash shortages that will affect delivery of activities?
Internal / external politics - can we expect any effect?
What if the key project person(s) leaves the organisation?
Notes: NOTE N°1: TITLES OF SLIDES ARE WRITTEN USING CENTURY GOTHIC 24, TESIM PURPLE COLOUR, NOT IN CAPITALS. TEXT IS JUSTIFIED LEFT AND ALIGNED WITH END OF LINE BELOW.
NOTE N°2: HEADINGS ARE WRITTEN IN CAPITALS IN BOLD TESIM BLUE, CENTURY GOTHIC 24. THEY ARE CENTRED AND NOT UNDERLINED

## Slide 17
Risks in the project
Not all risks will be present in a given project
Important to understand where the high risks are
Agree in the project how to address them
Risk management will differ from project to project
Notes: NOTE N°1: TITLES OF SLIDES ARE WRITTEN USING CENTURY GOTHIC 24, TESIM PURPLE COLOUR, NOT IN CAPITALS. TEXT IS JUSTIFIED LEFT AND ALIGNED WITH END OF LINE BELOW.
NOTE N°2: HEADINGS ARE WRITTEN IN CAPITALS IN BOLD TESIM BLUE, CENTURY GOTHIC 24. THEY ARE CENTRED AND NOT UNDERLINED

## Slide 18
Risks in the project
On projects with a low-complexity, the project manager(s) may informally track risks that are considered important.
On more complex projects, the project management team may develop a list of risks perceived to be higher risk and track them during project.
Good internal control can reduce risks significantly!

## Slide 19: Setting up internal control system, accounting and reporting mechanisms
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 20
Keys to financial management
5 keys to financial management
1. Careful budgeting
2. Rigorous external checks
3. Regular reporting
4. Effective internal control
5. Reasonable care
Key | Why
Careful budgeting | Realistic budget and adequate follow-up enable to measure performance and identify and prevent potential problems.
Rigorous external checks | These checks ensure that the beneficiary is in compliance with rules, laws and regulations and protects against irregularities, fraud and corruption.
Regular reporting | An adequate system of regular internal reporting ensures that the project is meeting its financial goals and objectives.
Effective internal control | Internal control is a cornerstone of financial management in any organisation and all ENI CBC beneficiaries are entitled to comply with its basic principles.
Reasonable care | Each beneficiary will take reasonable care of setting up an adequate financial management system, aiming at protecting the organisation against any misstatement, misuse or misappropriation of the EU funds.

## Slide 21: Internal control
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 22
Why internal control is a cornerstone of the project
Internal Control is designed to provide reasonable assurance that project is effective and efficient, that financial information is reliable and that the Contractual Conditions have been met.
If proper internal controls are not in place, there is a high risk that EU funds will not be spent as agreed in the Contract. Project assets may be lost and the use of funds may not be properly accounted for.
Key Message: ensure internal controls by all partners
Key Message: better safe than sorry; lack of internal control is a key risk

## Slide 23
Control environment
integrity, ethical values and the behaviour of key management staff;
management’s operating style;
management’s commitment and competence;
the organisational structure and assignment of responsibility and authority;
human resources policies and practices
By setting up the control environment, management “sets the tone” of the entire organisation, influencing the control consciousness of its staff.
By promoting key values such as integrity, ethics, transparency, competence and dedication to good management practices, management provides a framework for discipline and structure.

## Slide 24
Internal control related requirements
Requirement | Description | Basic tips
Segregation of duties | Duties of authorizing the expenditure and handling accounting and payments segregated | No transaction or chain of transactions is in the hands of a single person.
Absence of conflict of interest | All EU funded contracts prohibit conflicts of interest, confidential payments (e.g. secret commissions, bribes) and other unethical practices | Code of ethics needs to be written and understood by staff
Regular checks | Regular checks need to be established to ensure that the procedures are correctly implemented | Foresee effective approval points and assign responsibilities
Prevention of irregularities, fraud and corruption | Human resources policies need to include measures for prevention | Describe all responsibilities, procedures and tasks in writing (job description, manual of procedures, etc.)

## Slide 25: Accounting and record keeping
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 26
Accurately record all transactions
Income and expenditure must be recorded in separate accounting system or using a specific accounting code;
Follows national accountancy rules and standards;
Income and expenditure related to the project have to be easily traceable and identifiable.
Key message: Good financial management can ensure that the costs of the the project will be eligible!
Key message: Poorly organised record and document keeping system can put the project at risk when facing controls and audits!
Information, documentation and accounting records must be kept until, at least …

## Slide 27
An Excel sheet cannot be considered as accounting
List of transactions
Supporting documents
Ledger
Financial report
Budget
List of transactions
Financial report
Financial report
Double entry
Simple entry
Ensure easy reconciliation between accounting (and other IT records) and the reports.

## Slide 28: Reporting mechanisms
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 29
Reporting three dimensions
Communication
Accountability
(and payment claim)
Monitoring
(and decision-making)
Reporting cannot be seen as a formal requirement to receive the grant. Use it also :
to ensure regular monitoring and adequate strategic and operational decision-making
Use it as an internal and external communication tool
Look beyond the grant contract

## Slide 30
Some tips
Look at the template of final and interim reports as soon as possible! Any information needed for reporting has to be collected from the beginning;
Keep you accounting and activity monitoring system on an on-going basis;
Agree regular updates of information with your partners; reporting in multi-beneficiary projects is a team work!
Involve your auditors as soon as possible; when preparing the payment claim is too late to find a shared understanding of the rules.
Read carefully the reporting provisions in the grant contract

## Slide 31
Finance and activities go together
Ensure the link between activities and expenses!!
Financial supporting documents
Activity supporting documents
Project accounting
Financial report
Document repository
Activity report
And send the reports in due time!!

## Slide 32: National legal requirements impacting project delivery
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 33
Legal framework in Ukraine
National legislation
EU legislation + programme rules
Financing & Association Agreements
ENI CBC legal framework
Проект постанови про створення національної системи менеджменту та контролю програм прикордонного співробітництва Європейського інструменту сусідства на 2014 – 2020 роки

## Slide 34
National authorities and procedures in Ukraine
Institution | Role | Main tasks concerning beneficiaries
Ministry of Economy and Trade | National Authority | Registration Tax exemption Monitoring and support
Ministry of Finance | Control Contact Point | Set up of long list of auditors Quality control of expenditure verification reports Participation in on-the-spot checks by Managing Authority
Ukrainian Accounting Chamber | Member of the Group of Auditors | Participation in audit missions by Audit Authority
New roles & new responsibilities

## Slide 35
Procurement by Ukrainian beneficiaries
Public beneficiaries
National legislation (Prozorro)
Some additional requirements
Private beneficiaries
Prag
Some additional requirements

## Slide 36
Examples of additional requirements for procurement
Public beneficiaries | Private beneficiaries
Obligation of a tender committee with an odd number of members | Compulsory use of Prag procedures and templates
Check of exclusion criteria stipulated in EU legislation and request of a declaration on honour to tenderers | Additional requirements and templates are set for contracts below 20.000€
Additional information added to the one indicated in Order No 680 of the Ministry of Economy of Ukraine of 13 April 2016 for some usual tender documents | Additional requirements and templates are set for payments against invoice without contract (below 2.500€)
Some additional templates for tender documents (Prag is suggested as source of inspiration) | 
Detailed information will be available in guidelines under preparation

## Slide 37: Thank you! Any questions?